## Customer Stories - Master (hidden)
Client: CLIENT NAME
Master Customer Story |  |  |  | Total Hours Estimate
147
Epic | Customer Story | Suggested Implementation Path | Assumptions | Hours Estimate | Phase | POC
Pick and implement an SMS solution | 50Floor's customer experience team needs to send SMS messages throughout their customer lifecycle. This primarily centers on SMS messages triggered by deal properties and SMS messages that deliver NPS survey links. | Aptitude 8 validates HubSpot SMS gives the team what they need. If it does, deprecate Twilio and Skipio and complete the HubSpot SMS build. We suspect HubSpot SMS gives you want you need and will work because it allows you to send SMS in deal based workflows. | - 50floor team has already purchased HubSpot SMS - 50floor team has a current Twilio/Skipio account they use but haven't succesfully set up. Aptitude 8 will help 50floor's decide which tool is best based on needs. - 50floor team has already written most of the copy for the messages and therefore, A8 will not have to write much more. - Aptitude 8 will write the workflows for the SMS messages marked as "Now" in this sheet. | 20 | NEXT
Implement a lead scoring program | 50Floor wants to the ability to prioritize high quality leads primarily for sales rep assignment. However, this might also be for marketing purposes as well. | Use HubSpot contact score properties to assign numeric values to variables like household income and home value. Then, use calculation properties or a workflow to set a lead tier property: 1,2,3 based on the numeric value range. |  | 10 | NEXT
Implement a lead assignment algorithm | 50Floors estimates that by assigning the best leads to the best reps will dramatically increase profit margins. So, they seek a lead assignment algorithm that weighs sales rep availability with an apppointment time, the market, the capacity of the sales rep, and the quality of the lead. | - Oasis calculates some variables for us then sends it to HubSpot for a custom coded action(s) to ultimately apply the lead assignment. | - Currently, lead assignment is manual and varied amongst markets. This leads to leads going unassigned, the best sales reps aren't at capacity, and the leads are not assigned based on a lead interest/sales person skillset match. - An Oasis to HubSpot and HubSpot to Oasis integration will need to exist in order to pass the correct inputs to HubSpot to calculate the assignment as well as send the ERP the results for commission purposes. - 50Floor will run the following calculations on their end so it's output can be stored in HubSpot: GPL, Geographic location proximity. - 50Floor will ensure the stable access to Oasis and acknowledges if inputs aren't passed to HubSpot the lead assignment flow will break. Potentialy requiring manual imports to HubSpot as a workaround when broken. - 30 hours to write, 10 to test, 25 for revisions and change in scope, 10 hours for launch/launch support. | 75 | NOW
Reporting and Dashboards | 50Floor aims for enhanced reporting capabilities in HubSpot for their lead assignment automation. | Aptitude 8 will configure up to (6) custom reports and (3) dashboards for leadership and sales managers. |  | 8
Project Management | Aptitude8 includes dedicated Project Management for all projects and retainers in order to ensure the highest standards in quality and delivery | Aptitude 8 will assigned a dedicated delivery lead to this project, to manage the timeline, hours, and deliverables |  | 17
Contingency | Hours we require in order to handle any items that arise, larger than anticipated scope, or dependencies without necessitating a change order |  |  | 17

## Customer Stories - SMS
Client: 50Floor
Master Customer Story |  |  |  | Total Hours Estimate
Epic | Customer Story | Suggested Implementation Path | Assumptions | Hours Estimate | Phase | POC | Context:
Auto-send 1-1 SMS to customers based on triggers in HubSpot and Oasis. | 50Floor needs to be able to have the functionality of sending automatic text messages based on triggers in HubSpot. (Ex. Text sent day of the appointment) | Define the specific cadence of the workflows and what their triggers would be specifically based on their process. As well as define the exact wording of messaging 50Floor wishes to do. After collaboratively defining the criteria for the workflows and messaging, Aptitude 8 would set up the workflows with the agreed upon trigger criteria with the SMS step including the appropriate verbiage. | - HubSpot workflows will be used - 50Floor has a Salesmsg account set up with Aptitude 8 receiving an invitation - Salesmsg integration with HubSpot is set up by Aptitude 8 - 50Floor & Aptitude 8 will collaborate on trigger cadences, and best practice based on the intended goal - 50Floor will create the messaging on what their customers receive based on that goal, Aptitude 8 can provide insight as needed - Maximum of 6 workflows | 15 | NOW
Auto-send surveys via SMS to customers after specific events (call center touchpoints, rep appointments). | 50Floor needs to be able to send surveys via text message to customers after specific points in their process. (Ex. When the deal closes out) | 50Floor would define each specific point in the process that they'd want a survey to be sent to the customer as well as the messaging. Aptitude 8 can provide insight as necessary. 50Floor & Aptitude 8 will define what survey platform should be utilized with this process. Once those are defined, 50Floor & Aptitude 8 will collabortively define what the triggers would be for sending the surveys based on their process. Aptitude 8 then will create the workflows in HubSpot with the agreed upon triggers, as well as utilizing the appropriate verbiage for the messaging. | - 50Floor has a Salesmsg account set up with Aptitude 8 receiving an invitation - Salesmsg integration with HubSpot is set up by Aptitude 8 - HubSpot workflows could be used, or Zapier could be involved - Survey platform gets defined by 50Floor & Aptitude 8 (ex. Surveymonkey) - 50Floor defines specific points in the process for surveys to be sent - 50Floor & Aptitude 8 will collaborate on the trigger cadences, and the best practice based on the intended goal - Aptitude 8 will set up the HubSpot workflows, and/or Zaps to support this process - Maximum of 4 workflows and one Zap | 12 | NOW
Auto-send marketing nurture SMS to prospects who engage or do not engage in specific ways | 50Floor needs to be able to send nuture messages to customers who either haven't engaged, stopped engaging, or fall off during the process. (Ex. Had an appointment but didn't schedule an install) | 50Floor would define each of the set places in the process where an automated text message would be needed to nudge the customer with Aptitude 8 assisting and providing best practice as necessary. Also 50Floor and Aptitude 8 will collabortively define what the triggers would be based on the process. 50Floor would also create the messaging for the specific events, with Aptitude 8's assistance where applicable. Once those are defined, Aptitude 8 will implement the workflows with the defined triggers based on the process, and set up the SMS step with the appropriate verbiage defined by 50Floor based on the specific event occuring. | - HubSpot workflows will be used - 50Floor has a Salesmsg account set up with Aptitude 8 receiving an invitation - Salesmsg integration with HubSpot is set up by Aptitude 8 - 50Floor will define all the places in the process a nuture message would be appropriate - 50Floor & Aptitude 8 will collaborate on trigger cadences, and best practice based on the intended goal - 50Floor will create the messaging on what their customers receive based on that goal, Aptitude 8 can provide insight as needed - Maximum of 6 workflows | 15 | NOW
Trigger events in HubSpot and Oasis based on the text in SMS replies from customers. | 50Floor needs to be able to have SMS replies trigger automation in HubSpot, creating events or storing inputted information in fields if necessary. | Define all the specific events that are intended to happen or what's to be stored in HubSpot based on SMS responses. After collabortively defining what's required for specific SMS responses in the process, Aptitude 8 would set up the Zaps that integrate with Salesmsg to pull responses based on the inbox and set them up to active HubSpot workflows (if applicable) and/or create events in HubSpot on the specific record. | - 50Floor has a Salesmsg account set up with Aptitude 8 receiving an invitation - Salesmsg integration with HubSpot is set up by Aptitude 8 - Zapier will grab the responses and trigger event creations and/or workflow enrollments in HubSpot - HubSpot workflows can be involved to reduce Zapier task usage - 50Floor will gain a Zapier account with the Teams subscription (task count will be determined later on) and invite zach@aptitude8.com to the account as an Admin to grant access to the rest of the team as necessary - Aptitude 8 will set up the Zaps required to achieve the intended goal - 50Floor & Aptitude 8 will collaboratively define the events necessary to occur in HubSpot based on specific SMS responses - Maximum of 6 workflows and 4 Zaps | 25 | NOW
Project Management | Aptitude8 includes dedicated Project Management for all projects and retainers in order to ensure the highest standards in quality and delivery | Aptitude 8 will assign a dedicated delivery lead to this project, to manage the timeline, hours, and deliverables | This includes weekly sprint meetings for the duration of the project term to keep teams aligned and progress moving forward Includes project provisioning, communication management, and timeline adjustments as needed to keep the project on track | 10 | NOW
Contingency | Hours Aptitude 8 requires in order to handle any items that arise, larger than anticipated scope, or dependencies without necessitating a change order | All non-epic tasks will be recorded under this epic |  | 7 | NOW

## Customer Stories - Next
Client: 50Floor
Master Customer Story |  |  |  | Total Hours Estimate
10
Epic | Customer Story | Suggested Implementation Path | Assumptions | Hours Estimate | Phase | POC
Lead Scoring Program Discovery | 50Floor wants to the ability to prioritize high quality leads primarily for sales rep assignment. However, this might also be for marketing purposes as well. | Use HubSpot contact score properties to assign numeric values to variables like household income and home value. Then, use calculation properties or a workflow to set a lead tier property: 1,2,3 based on the numeric value range. |  | 10 | NEXT

## Change Order
Client: 50Floor
Master Customer Story |  |  |  | Total Hours Estimate
--- |  |  |  | 58 | 13050
Epic | Customer Story | Suggested Implementation Path | Assumptions | Hours Estimate | Phase | POC
Route Planning Requirements Gathering, Solution, & Project Plan | 50Floor requires clear business rules and success criteria to be written for a successful project. | Document in a shared lucidchart and google docs/sheets to ensure success of project. Clearly outline what is not in scope. | - We will use up to 12 hours, pulled from contingency hours from the original SOW, to finalize the route planning piece and how it impacts the integration method in question: HubSpot or Zapier | 0 | NOW
Route Planning Feature | 50Floor needs to consider job address, the location of a booked appointment, in their lead assignment automation in order to optimize the route a sales rep has each day in order to prevent long travel times in short time frames for their sales reps. | Aptitude 8 will have a developer evaluate our two options to integrate Oasis andHubSpot: an iPaas software like Zapier or HubSpot integration features like custom code actions. Based on 50Floor's requirements and the developers evaluation Aptitude 8 will recommend a integration method that supports 50Floor today and beyond. | - If slots are adjacent, no more than 20 miles between addresses - Adjacent is defined as a time slots that occurs after the preceding time slot. Example: 9-11 am and 11am-1pm time slots are adjacent. - A job address should be no more than 60 miles from home address of the sales rep for first appointment - Tier 1 reps should get their individual maximum leads before tier 2 is considered - Tier 2 reps should get their individual maximum leads before tier 3 is considered - No more than 20 miles between appointments for adjacent time slots - Time slots are 9-11am, 11am-1pm, 1pm-3pm, 3pm-5pm, 6pm-8pm (last one not on Saturdays, no appts Sundays) - The first appointment can’t be more than 60 miles away from sales rep’s home address (no matter which time slot) - 50Floor will make data accessible in a format required to make this possible. Examples: Expose Sales Rep home address, availability, and appointments. | 50 | NOW
Contingency Hours | Hours we require in order to handle any items that arise, larger than anticipated scope, or dependencies without necessitating a change order |  | - These are added to account for additional complexity that comes with adding route planning. | 8 | NOW