## Salesforce Integration
Cars - Salesforce Integration Optimization & Deduplication
| Workstream | Customer Story | Suggested Path | Assumptions | Low Hours | High Hours | Potential Variance | Project Phase | POC
| Strategy Work | [5 empty] | Standard | NOW
SW-1 | Data Modeling & Transformation Strategy | PracticeTek needs to 1) understand what data model is required to set the foundation of additional portal migrations and integrations and 2) understand the transformation to existing data to ensure it's a clean start to the new stack. | Run discovery to understand high-level mapping needs, finalize objects, relationships, and properties for integration purposes and for future growth. | - Data model and process map for each business unit - Clearly atriculated overview of data issues and impacts of business - Requirements should clearly indicate what is a non-negotiable requirement for the MVP phase, what is phase 2 and beyond, and acceptance criteria to complete the work successfully - Information gathered will support the "Integration Overview" | 10 | 15
SW-2 | Customer Journey Mapping | PracticeTek needs a mechanism to reflect the customer journey for each brand for this first phase: ChiroTouch, RevolutionEHR, and ClinicSource. | Use this as discovery and solutioning time to address lifecycle stage per brand and lead score per brand requirements | - Map customer journey for RevolutionEHR and ClinicSource into their new portal: Chirotouch. This must consider many more brands coming into Chirotouch's portal in the future. - Define the most appropriate solution for representing each brand's (3) customer journey and up to 1 lead score using the Lead Score feature in HubSpot per brand. Does not include a custom coded solutions for lead scoring. | 12 | 15
SW-3 | Solution Engineering | PracticeTek needs Aptitude 8's expertise navigating a highly complex salesforce integration. | Walk PracticeTek team through solution overview workshops once Data Modeling, Portal Migration, and Salesforce Integration requirements have been confirmed. | - Up to 60 hours - Aptitude 8 will walk PracticeTek through detailed solution options for the salesforce integration and portal migration work - Aptitude 8 will detail new processes in the new portal and how they map to automations being migrated + describe how those automations need to change, if at all | 40 | 60
SW-4 | Integration Overview Deliverable | PracticeTek requires their integration requirements are clearly defined before starting on the integration so success criteria and approach are clear. | Organize the output of requirements confirmation and solutioning workshops into one document for PracticeTek approval. | - Aptitude 8 will create an integration requirements document to represent the bidirectional Salesforce<> HubSpot integration. Example Deliverable: https://docs.google.com/document/d/1vqbnIEoDbFStBk6wwTQQZlxlDxujdIVEW4jJHEEJ980/edit?tab=t.0 | 3 | 5
SW-5 | Project Strategy & Planning | PracticeTek needs Aptitude 8's expertise crafting a project strategy to ensure timelines are met and the project is delivered on time. | Create a gantt chart with dependencies specified | - Final project plan created and agreed will be created in Clickup - Aptitude 8 will work in Asana, too, because PracticeTek's broader Project Harmony is defined and managed there | 5 | 10
| HubSpot Re-Configuration | [5 empty] | Standard | NOW
HR - 1 | Implement Data Model | PracticeTek needs a foundational data model built in order to facilitate future portal migration efforts and integrations. | Use the unified data model created in the solution engineering phase as a spec to build out new properties, association labels, and objects. | - Up to 2 new custom objects: 'Propensity Custom Object' and another custom object to facilitate upsells and how they impact a lifecycle stage of a contact within a certain brand. - Up to 500 custom properties across all objects - Up to 20 new association labels - Aptitude 8 will not make changes to Salesforce, PracticeTek will be instructed by Aptitude 8 to do this when applicable. | 15 | 20
HR - 2 | Customize Record Layouts | PracticeTek wants to show the right information to the right people at the right time on the right object so their users can have a simpler process to follow in their portal. | Use the wire frames produced in the solution engineering phase as truth for what record customization needs to exist. | - Non-coded record customization for Contact, Company, Deal, and up to 2 custom objects - Up to 3 team/group views per object - Includes left, middle, and right pane customizations - No custom coded CRM cards | 15 | 20
HR - 3 | Implement Users & Permissions | PracticeTek needs permissions setup to align with their business needs so that the correct teams have visibility where they don't today and continue to segment visibility where teams shouldn't have it. | Use the permissions exercise as source of truth for what permissions to implement and how/when to bring in user groups. | - This is an execution task defined defined by the Requirements and Solutioning worksteam - Aptitude 8 to support permissions and security for up to 120 seats across 18 teams (ChiroTouch and RevolutionEHR teams only). | 8 | 12
HR - 4 | Implement Business Units | PracticeTek needs to configure 2 business units to ensure contacts and assets are properly attributed to the correct brand. | Implement BUs for ChiroTouch, RevolutionEHR, and ClinicSource. | - Up to 5 hours for each business unit - ClinicSource will not have any assets to tie their business unit, only records and related properties. | 16 | 18
HR - 5 | Implement Customer Journey Solution Per Brand | PracticeTek desires a clear way to track where a person sits in a brand's customer journey. Ideally, this is a templatized-like approach so they can use the framework for future brands migrated to this HubSpot portal. | - Detail why one lifecycle stage property will likely not meet PracticeTek requirements - Present custom object based solutions - Navigate naunces of creating custom automation to replicate Lifecycle Stage OOTB functionality | - Up to 8 hours of customer journey automation per brand | 10 | 16
HR - 6 | Implement Lead Score Solution Per Brand | PracticeTek requires a lead score framework that can be used for ChiroTouch and RevolutionEHR and ideally re-purposed for future brands migrated to this HubSpot portal. | - Pick a lead scoring mechanism: property score field vs. lead score feature - Use thresholds to surface contacts to sales, use in email campaigns, and other marketing ops functions | - Up to 3 hours per lead score and up to 3 hours to creating supporting automations to leverage the scoring field, per brand | 6 | 12
| Data Transformation | [5 empty] | High | NOW
DT-1 | Resolve Duplicates & Unify Data Model | PracticeTek requires data transformation to create a smooth data unification process. | Resolve non-legitimate duplicates. Identify 'which field wins' logic. Programmatically update records based on specs. | - Up to 10 hours for Aptitude 8 advisory time to consult PracticeTek & Coastal Cloud - Up to 70 hours for Aptitude data transformation - Transformation on up to 750,000 records between ChiroTouch and RevolutionEHRs portals - Aptitude 8 does not include files/attachments to records part of this scope | 60 | 80
DT-2 | Migrate ClinicSource Records from Salesforce | PracticeTek needs to import ClinicSource records into HubSpot and have them tied to their business unit so they can be easily leveraged in future phases. | Aptitude 8 recommends fetching and creating records via API so the records are quickly migrated under a tight deadline. | - See ClinicSource Record Migration Tab for record counts and migration scope - Aptitude 8 will migrate records via API - Aptitude 8 does not include files/attachments to records part of this scope - Records migrated won't exceed the objects listed and 60,000 total records for this brand | 12 | 15
| System Integration - Salesforce | [5 empty] | High | NOW
SF-1 | Integration Infrastructure | PracticeTek requires Aptitude 8 to setup the infrastructure required to power the bidirectional sync between Salesforce and HubSpot. | Contingent on integration method picked to manage the sync. Detailed in Integration Overview deliverable. | - Create web services or set up ipaas infrastructure - Mechanism to orchestrate API calls, manage authentication, manage volume (queueing) - Optimize for changes over time - Optimize error handling/monitoring - Aptitude 8 won't make changes to PracticeTek's Salesforce instance but will advise changes required | 50 | 70
SF-2 | Object Sync (5) - Bi-Directional | PracticeTek desires as close to real-time sync between systems for 5 standard objects to ensure marketing can handoff leads to sales and sales data can inform marketing efforts. | The solution must give PracticeTek adequate ability to identify and troubleshooting errors as well as modify field mappings and logic. | - Sync Leads, Contacts, Accounts, Companies, Tasks (activities), and Opportunities - PracticeTek expects to have control over field mappings and record sync criteria (inclusion lists) | 75 | 125
SF-3 | Custom Object Sync (2) - Bi-Directional | PracticeTek desires as close to real-time sync between systems for 2 custom objects to ensure sales data can inform marketing efforts. | The solution must give PracticeTek adequate ability to identify and troubleshooting errors as well as modify field mappings and logic. | - Sync 'Propensity' and one other custom object dedicated to facilitating upsell opportunities - PracticeTek expects to have control over field mappings and record sync criteria (inclusion lists) | 30 | 50
SF-4 | User Acceptance Testing (UAT) | PracticeTek needs thorough quality assurance and user acceptance testing to ensure functionality, performance, and user experience meets expected standards respective to the integration and native HubSpot workflows. | Both teams will collaborate on a UAT proceed to ensure all requirements are meant and there is not failed logic before the integration is live with production data. | - Aptitude 8 to conduct internal testing prior to handing off to the client - Aptitude 8 to provide PracticeTek with a UAT document and instructions on how to perform tests | 50 | 90
SF-5 | Launch | PracticeTek requires Aptitude 8 to run the launch of the new integration. | Refer to the launch requirements in the integration overview deliverable to ensure alignment across all relevant parties. | - PracticeTek understands they play a critical role in a successful launch. Namely, ensuring systems and people are prepared for the transition. | 16 | 24
| Training & Documentation | [5 empty] | Low | NOW
TD-1 | Training |  |  | - Up to 25 hours of training for end users, admins, business systems team, and leadership | 20 | 25
TD-2 | Documentation |  |  | - Documentation on ALL custom configuration completed by Aptitude 8 - Up to 20 hours | 15 | 20
| Estimated Implementation Subtotals |  |  |  | 468 | 702
| Project Management |  |  |  | 117 | 175.5
Project Kickoff & Closeout
Recurring Project Check-ins
Administration
|  |  |  | Estimated Investment Totals | 585 | 877.5
Post-Launch Support
| Post Go-Live Support | 25 hours dedicated to post go-live support over three months. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.)
|  |  |  | Total Estimated Hours | 732
|  |  |  | Total Project Estimated Investment | 179340
|  |  |  | Total Investment with Post-Launch Support | 195840

## CO - Sysetem Integration- Sales
System Integration - Salesforce | [5 empty] | High | NOW
Integration Infrastructure | PracticeTek requires Aptitude 8 to setup the infrastructure required to power the bidirectional sync between Salesforce and HubSpot. | Contingent on integration method picked to manage the sync. Detailed in Integration Overview deliverable. | - Create web services or set up ipaas infrastructure - Mechanism to orchestrate API calls, manage authentication, manage volume (queueing) - Optimize for changes over time - Optimize error handling/monitoring - Aptitude 8 won't make changes to PracticeTek's Salesforce instance but will advise changes required | 50 | 70
HubSpot GUI Setup | PracticeTek requires a functional GUI for management of the SalesForce integration by non-devs. The interface should be flexible but limit access to management by permission groups. | GUI will be HubSpot based utilizing a combination of custom objects to maintain object and property mapping parameters. | - PracticeTek expects to have control over field mappings and record sync criteria (inclusion lists) | 15 | 25
Backend Application Development | PracticeTek desires as close to real-time sync between systems for 5 standard and 2 custom objects to ensure sales data can inform marketing efforts and had off leads to sales. | Aptitude 8 should build a flexible integration framework that is customizable by the end-user, and as such no hard coded mappings or filter rules are included in the logic to create scalability and flexibility. | - Sync Leads, Contacts, Accounts, Companies, Tasks (activities), and Opportunities - Sync 'Propensity' and one other custom object dedicated to facilitating upsell opportunities - PracticeTek expects to have control over field mappings and record sync criteria (inclusion lists) | 90 | 150
User Acceptance Testing (UAT) | PracticeTek needs thorough quality assurance and user acceptance testing to ensure functionality, performance, and user experience meets expected standards respective to the integration and native HubSpot workflows. | Both teams will collaborate on a UAT proceed to ensure all requirements are meant and there is not failed logic before the integration is live with production data. | - Aptitude 8 to conduct internal testing prior to handing off to the client - Aptitude 8 to provide PracticeTek with a UAT document and instructions on how to perform tests | 50 | 90
Launch | PracticeTek requires Aptitude 8 to run the launch of the new integration. | Refer to the launch requirements in the integration overview deliverable to ensure alignment across all relevant parties. | - PracticeTek understands they play a critical role in a successful launch. Namely, ensuring systems and people are prepared for the transition. | 16 | 24

## Portal Migration
PracticeTek - Portal Migration
Master Customer Story
PracticeTek's business currently consists of 18 distinct brands, each operating independently with its own customer relationships across various retail healthcare solutions, such as patient acquisition, revenue cycle management, and practice management systems. They are shifting from a brand-centric approach to a market-led strategy, organizing around core verticals like optometry, chiropractic, etc. This transformation requires a more sophisticated segmentation strategy that evaluates customers based on their current solutions, identifies upsell opportunities, and aligns offerings to maximize value within each vertical. The ultimate goal is to move away from a fragmented brand-driven structure toward a unified, market-focused approach that delivers more strategic and scalable customer engagement.
| Workstream | Customer Story | Suggested Path | Assumptions | Low Hours | High Hours | Potential Variance | Project Phase | POC
. | Requirements & Solutioning Workshops | [5 empty] | Standard | NOW
SW-3 | Asset Audit | PracticeTek needs to conduct an audit to understand which assets need to move, which don't, and in what order to ensure business is not interrupted. | Use a guided Asset Audit template and exercise with the RevolutionEHR team to ensure high priority assets are brought over first. | - Aptitude 8 will guide and advise the PracticeTek team to create an accurate final spec on which assets need to be migrated to Chirotouch' portal. - PracticeTek should expect to spend signifigant time on this task at the beginning of the project so timelines are met | 10 | 20
SW-4 | Portal Migration Strategy & Planning | PracticeTek needs Aptitude 8's expertise crafting a project strategy to ensure timelines are met and the project is delivered on time. | Create a gantt chart with dependencies specified | - Final project plan created and agreed will be created in Clickup - Aptitude 8 will work in Asana, too, because PracticeTek's broader Project Harmony is defined and managed there | 5 | 8
. | Asset Migration - HubSpot | [5 empty] | High | NOW
AM -1 | Portal Asset Migration | PracticeTek Marketing team needs to migrate RevolutionEHR's HubSpot assets to Chirotouch' HubSpot portal. | Use a blended approach of automation and manual creation of assets where automation capabilities lack. | - Aptitude 8 will migrate the assets counts (and complexity) listed in the Portal Consolidation Tab. - These assets will only move from Revolution EHR's portal to the ChiroTouch portal. - This does not include all assets identified as a rough estimate by the PracticeTek team. PracticeTek should assume their team will be migrating some smaller percentage of the assets identified. Aptitude 8 does the heavy lifting. - Migration methods include HubSpot's new Multi-Account Asset Replicator feature, custom code, and manual efforts to move assets not easily moved by API. | 295 | 450
. | Training & Documentation | [5 empty] | Low | NOW
TD-3 | Training |  |  | - Up to 15 hours of training for end users, admins, business systems team, and leadership | 10 | 15
TD-4 | Documentation |  |  | - Up to 15 hours of documentation of changes made to workflows and other assets | 10 | 15
| Estimated Implementation Subtotals |  |  |  | 330 | 508
. | Project Management |  |  |  | 82.5 | 127
Project Kickoff & Closeout
Recurring Project Check-ins
Administration
|  |  |  | Estimated Investment Totals | 412.5 | 635
. | Post-Launch Support
| Post Go-Live Support | 25 hours dedicated to post go-live support over three months. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.)
|  |  |  | Total Estimated Hours | 524
|  |  |  | Total Project Estimated Investment | 128380
|  |  |  | Total Investment with Post-Launch Support | 144880

## Estimate v2
Custom Salesforce Integration |  | Low | Low Cost | High | High Cost | Assumptions
P1 - Strategy | Data Modeling & Cleanup Strategy | 10 | 2450 | 15 | 3675 | Map data between portals, between salesforce and hubspot, align customer journey
| Solution Engineering | 40 | 9800 | 60 | 14700 | Enterprise Level Complexity for Custom Integration, Integration setup to support future portal migrations to winning HubSpot portal
| Project Strategy & Planning | 10 | 2450 | 15 | 3675
P2 - System Configuration | Create Data Model | 10 | 2450 | 15 | 3675 | Thousands of custom properties, thousands of native properties
| Record Customization | 15 | 3675 | 20 | 4900
| Implement Users & Permissions | 15 | 3675 | 20 | 4900
| Implement Business Units | 16 | 3920 | 20 | 4900
P3 - Integration Implementation | Integration Infrastructure | 50 | 12250 | 70 | 17150
| Object Sync (5) - Bi-Directional | 75 | 18375 | 125 | 30625 | Leads, Contacts, Accounts, Companies, Tasks (activities), and Opportunities
| Custom Object Sync (2) - Bi-Directional | 30 | 7350 | 50 | 12250 | Practicetek - Stax, Practicetek - Subscription Histories
| Data Cleanup | 60 | 14700 | 80 | 19600 | Up to 1.5 million records from objects included in sync, no files. Logic required to unify contacts and companies, implement which field wins, etc.
| Integration Testing (UAT) | 50 | 12250 | 90 | 22050
| Launch | 16 | 3920 | 24 | 5880
| Sub total | 397 | 97265 | 604 | 147980
| Project Management | 99.25 | 24316.25 | 151 | 36995
| Total |  | 121581.25 |  | 184975
Portal Migration - D to E |  | Low | Low Cost | High | High Cost | Assumptions
P1 - Strategy | Asset Audit | 10 | 2450 | 20 | 4900
| Project Planning | 5 | 1225 | 8 | 1960
P2- Asset Migration | Email Templates | 10 | 2450 | 20 | 4900 | Manually created, up to 6, low to medium complexity (no custom code)
| Emails | 100 | 24500 | 150 | 36750 | 980 emails recreated using HubSpot's new Multi-Account Asset Creator. See Serocke/Liz notes to the right: | Automated Marketing Email Migration Learnings
| Landing Page Templates | 10 | 2450 | 20 | 4900 | Manually created, up to 6, low to medium complexity (no custom code)
| Landing Pages | 15 | 3675 | 25 | 6125 | Up to 15 recreated manually, low to medium complexity (no custom code)
| Forms | 10 | 2450 | 15 | 3675 | Up to 100 forms recreated using HubSpot's new Multi-Account Asset Creator
| Lists | 15 | 3675 | 20 | 4900 | Up to 500 lists recreated via API
| Workflows | 50 | 12250 | 75 | 18375 | Up to 50 workflows with low to medium complexity (no custom code)
| Campaigns | 50 | 12250 | 75 | 18375 | Up to 100 campaigns, manually created
| Reports | 25 | 6125 | 35 | 8575 | Up to 25 custom reports, including data sets use cases
| Dashboards | 10 | 2450 | 15 | 3675 | Up to 10 custom dashboards created
| Sub total | 310 | 75950 | 478 | 117110
| Project Management | 77.5 | 18987.5 | 119.5 | 29277.5
| Total |  | 94937.5 |  | 146387.5
Phase 1 Total Estimate |  | Low | High
| Salesforce Integration | 121581.25 | 184975
| Portal Merge - D to E | 94937.5 | 146387.5
| Total | 216518.75 | 331362.5

## Copy of Overview
PracticeTek - SF Custom Integration
Master Customer Story
PracticeTek aims to enhance their marketing automation functionality by optimizing their HubSpot-Salesforce integration. They prioritize automation of sales pipelines and customization of quotes to improve operational efficiency and customer engagement. A strategic partnership is sought for long-term optimization and scalability of their CRM ecosystem. PracticeTek end goal is a cohesive, data-driven environment that supports growth and adapts to evolving business needs.
| Workstream | Customer Story | Suggested Path | Assumptions | Low Hours | High Hours | Potential Variance | Project Phase | POC
. | Requirements & Solutioning Workshops | [5 empty] | Standard | NOW
| Requirements Gathering Workshops | PracticeTek needs Aptitude 8's strategic guidance to gather and organize requirements for each workstream. | Hold a workshop for each workstream to produce an output of a summary recommendations document including a detailed documentation of the current state as well as the future state. Conduct Discovery and Requirements Gathering Sessions & Produce a summary recommendations document including a detailed documentation of the current state as well as the future state with comprehensive diagrams detailing the integration points, data flow, and system requirements. | - x hours per workstream - User stories created for each workstream - Data model and process map for each workstream
| Systems Architecture | PracticeTek needs Aptitude 8's expertise to solve the requirements in each workstream and collectively in order to orchestrate a solution that meets all business objectives. | Run discovery to produce a field mapping document, finalize objects, relationships, and properties for migration purposes and for future growth. | - x hours per workstream - Decision Log artifact created as source of truth to decsions made - Process Maps, Data Model, Integration Requirements Document, Data Migration Plan* all finalized in this step
| Integration Requirements Document | PracticeTek requires their integration requirements are clearly defined before starting on the integration so success criteria and approach are clear. | Run an exercise to understand data mapping, sync criteria, integration method, error handling, API evaluation, and more. | - Aptitude 8 will create an integration requirements document to represent the [tool <> tool} integration. | 4 | 6
| Project Planning & Strategy | PracticeTek needs Aptitude 8's expertise crafting a project strategy to ensure timelines are met and the project is delivered on time. | Create a gantt chart with dependencies specified | - Final project plan created and agreed will be created in Clickup
| Requirements Gathering Workshops | PracticeTek needs Aptitude 8's strategic guidance to gather and organize requirements for marketing. Along with a general understanding of future-state requirements after Phase One. | Hold 3-4 workshops for marketing and sales processes with an output of user stories and process maps.
| Systems & Data Architecture | PracticeTek needs Aptitude 8's expertise collect additional requirements specific to the integration to understand how data should flow between Hubspot & Salesforce. | Run discovery to understand high-level mapping needs, finalize objects, relationships, and properties for integration purposes and for future growth.
| Project Planning & Strategy | PracticeTek needs Aptitude 8's expertise crafting a project strategy to ensure Phase 1 requirements are met and the project is delivered on time. | Create a gantt chart with dependencies specified
. | HubSpot Implementation - Data Model and Settings | [5 empty] | Standard | NOW
| Implement Data Model | PracticeTek would like to streamline operations, improve reporting, and align marketing and sales activities effectivel within HubSpot. | Use the data model produced in the Requirements & Solutioning phase as truth for what new objects, fields, and association labels need to exist. | - This is an execution task defined by the Requirements & Solutioning deliverables | 10 | 12
| Customize Record Layouts | PracticeTek wants to show the right information to the right people at the right time on the right object so their users can have a simpler process to follow in their portal. | Use the wire frames produced in the Requirements & Solutioning phase as truth for what record customization needs to exist. | - This is an execution task defined by CRM Architecture deliverables - Contact, Company, Deal, and up to 2 custom object record customization - Up to 3 team/group views per object - Includes left, middle, and right pane customizations - No custom coded CRM cards | 7 | 10
| Implement Users & Permissions | PracticeTek needs permissions setup to align with their business needs so that the correct teams have visibility where they don't today and continue to segment visibility where teams shouldn't have it. | Use the permissions exercise as source of truth for what permissions to implement and how/when to bring in user groups. | - This is an execution task defined defined by the Requirements and Solutioning worksteam - Aptitude 8 to support up to 25 seats across multiple teams | 2 | 4
. | HubSpot Implementation - Sales Hub | [5 empty] | Standard | NEXT
. | HubSpot Implementation - Marketing Hub | [5 empty] | Standard | LATER
. | Data & Asset Migration - {Name of System} | [5 empty] | High | NOW
. | System Integration - {Name of System} | [5 empty] | High | NOW
. | Training & Documentation | [5 empty] | Low | NOW
| End-User Training |  |  |  | 18 | 21
# of Sales or Service Seats
| Training Documentation |  |  |  | 8 | 10
| Estimated Implementation Subtotals |  |  |  | 49 | 63
. | Project Management |  |  |  | 9.8 | 12.6
Project Kickoff & Closeout
Recurring Project Check-ins
Administration
|  |  |  | Estimated Investment Totals | 58.8 | 75.6
. | Post-Launch Support
| Post Go-Live Support | 30 hours dedicated to post go-live support. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.)
|  |  |  | Total Estimated Hours | 67.2
|  |  |  | Total Project Estimated Investment | 16464
|  |  |  | Total Investment with Post-Launch Support | 23064

## RevolutionEHR Asset Migration
Brand Name: RevolutionEHR
Marketing |  |  | Records |  |  | Platform Setup |  |  | Technical Setup
Tool | # in existing system | Assumptions | Tool | # in exsisting system | PracticeTek Notes | Tool | # in exsisting system | PracticeTek Notes | Tool | # in existing | PracticeTek Notes | Assumptions
Email template(s) | 6 | Basic-moderate. No code customization. | Contacts | 97257 |  | Custom Properties | 417 Contact Properties total - 162 custom 0 custom Cart Properties | 3 custom Deal properties, 23 Companies (289 total) | Custom Coded Actions |  |  | Not in scope
Historical Email(s) | 980 | Unclear on how many are A/B. Aptitude 8 will assume up to 10% of emails have B variants that will be manually created. Aptitude 8 to use Multi-Account Asset Migrator tool and custom scripts. | Companies | 12708 |  | # Users | 62 | I do not know if all of these will need to be transfered over | Other integrations? | 14 Integrations | I do not know if all of these will need to be transfered over | Not in scope
Landing page template(s) | 6 | Basic-moderate. No code customization. | Deals | 30574 |  | # Teams | 16 | I do not know if all of these will need to be transfered over
Landing Page(s) | 13 published/73 total/ 2 website pages | Up to 15 recreated manually, low to medium complexity (no custom code). PracticeTek not clear if they will come over. | Engagements (tasks, notes, calls, emails, meetings) | 9,642 tasks All calls: 52,188 records | I do not know if all of these will need to be transfered over
Forms | 178 | Up to 100 forms recreated using HubSpot's new Multi-Account Asset Creator | Custom Object 1
Lists | 1222 | Up to 500 lists recreated via API | Custom Object 2
Campaigns | 379 | Up to 100 campaigns, manually created
low/med complexity workflows | 193 turned on | Up to 50 workflows with low to medium complexity (no custom code)
Custom Reports | 54 | Up to 25 custom reports, including data sets use cases
Dashboards | 18 | Up to 10 custom dashboards created

## ClinicSource Record Migration
Brand Name: ClinicSource
Marketing |  |  | Records |  |  | Platform Setup |  |  | Technical Setup
Tool | # in existing system | Assumptions | Tool | # in exsisting system | PracticeTek Notes | Tool | # in exsisting system | PracticeTek Notes | Tool | # in existing | PracticeTek Notes | Assumptions
Email template(s) | 0 | Aptitude 8 will not migrate any assets. | Contacts | 16498 |  | Custom Properties |  |  | Custom Coded Actions |  |  | Not in scope
Historical Email(s) | 0 | Aptitude 8 will not migrate any assets. | Account | 8310 |  | # Users |  |  | Other integrations? |  |  | Not in scope
Landing page template(s) | 0 | Aptitude 8 will not migrate any assets. | Leads | 20878 |  | # Teams
Landing Page(s) | 0 | Aptitude 8 will not migrate any assets. | Opportunities | 12371
Forms | 0 | Aptitude 8 will not migrate any assets.
Lists | 0 | Aptitude 8 will not migrate any assets.
Campaigns | 0 | Aptitude 8 will not migrate any assets.
low/med complexity workflows | 0 | Aptitude 8 will not migrate any assets.
Custom Reports | 0 | Aptitude 8 will not migrate any assets.
Dashboards | 0 | Aptitude 8 will not migrate any assets.

## PracticeTek Total Estimates - R
Marketing |  |  | Records |  |  | Platform Setup |  |  | Technical Setup
Tool | # in existing system | Notes | Tool | # in exsisting system | Notes | Tool | # in exsisting system | Notes | Tool | # in existing | Notes
Email template(s) | 78 |  | Contacts | 831920 |  | Custom Properties | 118 | 12298 | Custom Coded Actions | 0
Historical Email(s) | 4853 |  | Companies | 507369 |  | # Users | 377 | Needs cleanup & review | Other integrations? | 76 | Needs cleanup & review
Landing page template(s) | 93 |  | Deals | 136927 |  | # Teams | 30
Landing Page(s) | 467 | total publish & unpublished | Engagements (tasks, notes, calls, emails, meetings) | 106,917 Tasks
Forms | 1058 | Needs cleanup & review |  | 55,628 Calls
Lists | 2847 | Needs cleanup & review
Campaigns | 987 | Needs cleanup & review | Custom Object 1 | Practicetek - Stax
low/med complexity workflows | 1384 |  | Custom Object 2 | Practicetek - Subscription Histories
med/high complexity workflows | 0
Custom Reports | 1628
Dashboards | 151

## Original Estimate (hidden)
Custom Salesforce Integration |  | Low | Low Cost | High | High Cost | Assumptions
P1 - Strategy | Data Modeling & Cleanup Strategy | 10 | 2450 | 15 | 3675
| Solution Engineering | 40 | 9800 | 60 | 14700 | Enterprise Level Complexity for Custom Integration
| Project Strategy & Planning | 10 | 2450 | 15 | 3675
P2 - System Configuration | Create Data Model | 10 | 2450 | 15 | 3675 | Thousands of custom properties, thousands of native properties
| Record Customization | 15 | 3675 | 20 | 4900
| Implement Users & Permissions | 15 | 3675 | 20 | 4900
| Implement Business Units | 16 | 3920 | 20 | 4900
P3 - Integration Implementation | Integration Infrastructure | 30 | 7350 | 40 | 9800
| Object Sync (5) - Bi-Directional | 75 | 18375 | 125 | 30625 | Leads, Contacts, Accounts, Companies, Tasks (activities), and Opportunities
| Custom Object Sync (2) - Bi-Directional | 30 | 7350 | 50 | 12250 | Practicetek - Stax, Practicetek - Subscription Histories
| Data Cleanup | 25 | 6125 | 45 | 11025 | Up to 1.5 million records from objects included in sync, no files. Logic required to unify contacts and companies, implement which field wins, etc.
| Integration Testing (UAT) | 25 | 6125 | 45 | 11025
| Launch | 16 | 3920 | 24 | 5880
| Sub total | 317 | 77665 | 494 | 121030
| Project Management | 63.4 | 15533 | 98.8 | 24206
| Total |  | 93198 |  | 145236