## Input
Display | Workstream | Service_Title | Customer_Story | Suggested_Path | Assumptions | Estimated_Low_Hours | Estimated_High_Hours | Contracted_Hours | Requires_Clarification | Function | Library_ID | Project_ID | Internal_Notes | Task_Link
Now | Mobilization | Project Setup | As a project team and client stakeholders, we want to align on project scope, timeline, deliverables, and stakeholders so that the project begins with shared clarity, expectations, and the right people involved. | Internal alignment session with Aptitude 8 delivery team to review sales conversations, reverse demo findings, and audit results External kickoff with Katie Macer, Director of Customer Experience, Senior Marketing Specialist, and key sales leadership (VP North America Sales, VP Technology Sales, Director Technology Sales, Chairman of the Board) Review organizational structure across regions (North America, Australia, Chile, Peru, Brazil, Southern Africa) Stakeholder mapping across 6 regional sales managers and 10+ total management levels Confirm access to key systems: HubSpot (Sales Enterprise, Service Professional/Enterprise, Marketing), Infor Syteline ERP documentation | Includes one internal alignment session and one external kickoff Client to provide NDA (already signed), ERP documentation, and any existing process documentation Stakeholder mapping covers regional managers and business unit leaders Excludes extensive role-based training during discovery phase | 8 | 12 | 10 | FALSE | Consulting
Now | Technical Assessment | HubSpot Portal Audit | As a technical consultant, I want to conduct a high-level HubSpot audit to determine current feature usage so that we understand existing portal capabilities and utilization. | Targeted deep dive into: Deal pipeline architecture and stage progression logic Ticket-to-Deal association workflows (quote request process) Conditional property dependencies per product line Custom object usage for draglines, haul trucks, shovels Association labels and relationship mapping Mobile optimization opportunities | Super Admin access already granted Focus on sales and service hubs given minimal marketing maturity Review existing workflows for optimization opportunities vs. complete rebuild Document current state for comparison to future state recommendations | 5 | 8 | 7 | FALSE | Development
Now | Technical Assessment | Data Quality & Structure Assessment | As a data analyst, I want to assess current data quality and structure so that we can identify cleansing and migration requirements prior to ERP integration. | Analyze deal data across 16 pipelines for consistency, required properties, and stage progression patterns Review company/contact association quality and customer classification (A/B/C/D tiers) Assess custom object data completeness (draglines database from third-party source) Evaluate target account usage and ICP definition gaps Review lifecycle stage alignment across 8 stages Identify duplicate records and data hygiene issues Map critical fields that will need to sync with Infor Syteline Cloud | Focus on sales and service data quality given business priority Review sample of deals across different pipelines and regions Client to provide ERP field mapping documentation when available Recommendations for data cleanse prior to integration project Excludes full data cleanse execution (can be scoped separately) | 10 | 12 | 11 | FALSE
Now | Technical Assessment | Integration Architecture Review | As a sales operations leader, I want to understand integration options between HubSpot and our future Infor Syteline Cloud ERP so that we can plan for seamless data flow and reduce manual processes. | Document current manual processes between systems (quote generation, order entry, invoicing) Review Infor Syteline Cloud API capabilities and integration readiness Identify critical data sync requirements (orders, quotes, customer data, pricing tiers) Evaluate middleware options (native HubSpot integration, iPaaS solutions) Define integration priorities aligned with 2026 ERP upgrade timeline Map current state manual workflows vs. future state integrated workflows | Infor Syteline Cloud upgrade timeline confirmed by client Client to provide ERP system documentation and API specifications Integration build-out will be separate project post-optimization Focus on planning and requirements gathering during assessment Assumes standard REST API availability from Infor Syteline | 12 | 16 | 14 | FALSE
Now | Process Discovery & Documentation | Sales Process Mapping by Product Line | As a sales leader, I want to document our distinct sales processes for each product line so that we can optimize HubSpot to support our actual selling motions rather than generic deal stages. | Repair Business (core, high volume, quick turnaround) Technology Products (Aardvark, Dragline Shovels, Haul Trucks, Wisdom - long cycle) Field Service, Distribution, Storage (varied complexity) Cross-functional Process Documentation | Includes interviews with sales managers across key regions Focus on 3-4 primary product lines given resource constraints Client to provide sample opportunities at various stages Excludes formal documentation; focus on practical HubSpot configuration Sessions conducted virtually given distributed team | 10 | 12 | 11 | FALSE
Now | Process Discovery & Documentation | Service & Support Process Discovery | As a customer experience leader, I want to document our customer service workflows so that we can determine whether HubSpot Service Hub is the right tool or if we need alternative solutions. | Review current ticket pipeline usage (Legal, Bids, Distribution Quotes, Repair Quotes, Claims, etc.) Analyze shared inbox workflows (quoting@flandersinc.com) Document internal ticketing vs. external customer service distinction Evaluate customer portal usage and customer self-service opportunities Review NPS survey program and feedback loop processes Assess knowledge base utilization and content strategy | Includes interview with Director of Customer Experience Review of Service Hub professional/enterprise feature utilization Focus on determining optimal use cases vs. misuse of Help Desk for internal workflows Recommendations may include alternative internal tools for operations coordination Customer portal review limited to current state assessment | 5 | 8 | 7 | FALSE
Now | Process Discovery & Documentation | Marketing Process & Lead Flow Assessment | As a marketing specialist, I want to understand how marketing can better support our account-based selling motion and leverage HubSpot capabilities despite limited resources. | Review current marketing asset creation and campaign execution (1-person team) Assess lead sources and lead flow (note: minimal inbound, relationship-driven business) Evaluate form strategy and trade show lead capture processes Review email marketing and sequence programs Analyze landing page performance and content strategy Assess marketing event tracking and campaign attribution Explore marketing agency coordination and collaboration needs | Single marketing specialist as primary stakeholder Focus on practical quick wins vs. comprehensive marketing transformation Recognize relationship-driven business model with limited inbound lead generation Marketing recommendations aligned with account-based approach Coordinate with marketing agency partner where applicable | 5 | 8 | 7 | FALSE
Now | Reporting & Analytics Strategy | Executive Dashboard Development | As the CEO and executive team, we want consolidated visibility into sales performance across regions and product lines so that we can make data-driven decisions as we scale the business. | Define key metrics by business unit (Repair, Field Service, Technology) Design CEO dashboard with consistent reporting across international operations Create regional performance dashboards for sales managers Build pipeline health and forecast accuracy reports Develop customer engagement and account health scoring Design activity-based reports (in-person meetings, calls, touchpoints by customer tier) Create quota attainment and rep performance views | Leverage existing quarterly review report structure as foundation Includes mock-ups of 3-5 key dashboards Focus on actionable metrics vs. vanity metrics Client to confirm data availability for historical trending Excludes complex revenue attribution modeling in initial phase | 8 | 12 | 10 | FALSE
Now | Reporting & Analytics Strategy | Sales Activity & Pipeline Management Reporting | As a sales manager, I want visibility into rep activity and pipeline health so that I can coach my team and forecast accurately in our long sales cycles. | Design activity tracking for field-based sales team (meetings, calls, site visits) Create pipeline velocity reports by product line Build deal age and stagnation alerts Develop forecast vs. actual analysis Design customer tiering and target account engagement reports Create quote turnaround time and bottleneck identification reports | Leverage existing deal count and revenue forecast reports as starting point Design for mobile visibility given field sales team Focus on leading indicators appropriate for multi-year sales cycles Includes recommendations for sales process improvements based on data Client to define acceptable activity thresholds by customer tier | 13 | 15 | 14 | FALSE
Now | Optimization Recommendations | Sales Hub Configuration Strategy | As a sales operations manager, I want a clear roadmap for optimizing our deal pipelines, properties, and automation so that HubSpot truly supports our field sales team rather than creating administrative burden. | Pipeline Architecture Recommendations Evaluate 16 pipeline structure (regional vs. product-based) Recommend consolidation opportunities while preserving regional nuances Design stage progression logic and probability mapping Define required vs. optional properties by pipeline/stage Property Optimization Audit 822 deal properties for utilization and relevance Recommend property rationalization and archiving strategy Design conditional property logic for mobile-friendly data collection Create property governance and naming conventions Automation Strategy Design playbooks for quote request submissions Build automated task routing to quoting team Create stage progression workflows with appropriate triggers Develop notification and escalation automations Design target account engagement sequences Mobile Optimization Recommend mobile app configuration for field sales Design simplified deal creation process Create mobile-friendly views and dashboards Develop voice note and photo attachment workflows | Recommendations based on best practices for complex B2B sales Prioritized roadmap (quick wins vs. long-term enhancements) Change management considerations given sales team resistance to complexity Focus on reducing manual data entry while maintaining data quality Includes mock-ups of key workflow examples | 13 | 15 | 14 | FALSE
Now | Optimization Recommendations | Service Hub Optimization Strategy | As an operations leader, I want to determine the right use of Service Hub for external customer service vs. finding alternative solutions for internal coordination so that we stop misusing ticketing for operations workflows. | Service Hub Appropriate Use Cases External customer inquiries and support requests Claims management and resolution tracking Customer portal optimization NPS program enhancement and feedback loop closure Knowledge base content strategy Internal Workflow Alternative Recommendations Evaluate quote request workflow alternatives (form-based, CRM card solutions) Recommend tools for operations/quoting/sales coordination Design cross-functional communication protocols Explore project management tool integration for engineering involvement Customer Experience Enhancement Design improved customer journey mapping Create proactive service workflows Build customer health scoring Develop retention and expansion playbooks | Recognize current misuse of Help Desk for internal operations Recommendations may include non-HubSpot tools for internal processes Focus on customer-facing service excellence Includes evaluation of Service Hub tier (Professional vs. Enterprise features) Client to confirm budget for additional tools if recommended | 12 | 16 | 14 | FALSE
Now | Optimization Recommendations | Marketing Hub Quick Wins Strategy | As a marketing specialist with limited resources, I want practical recommendations for leveraging HubSpot Marketing Hub to support our account-based selling motion and improve sales enablement. | Account-Based Marketing Foundation Sales Enablement Content Lead Source & Attribution Marketing & Sales Agency Collaboration | Focus on high-impact, low-effort tactics given 1-person team Leverage marketing agency for execution support Realistic expectations for inbound lead generation Recommendations support long sales cycle nurturing Includes coordination plan with sales sequences | 10 | 14 | 12 | FALSE
Now | Optimization Recommendations | Custom Object Strategy for Equipment Tracking | As a technology sales leader, I want to effectively track haul trucks, draglines, and shovels as individual assets so that we can identify cross-sell opportunities and target our selling efforts. | Review current custom object structure for draglines (206 records) Design scalable data model for 20,000+ haul trucks Create import strategy from third-party databases and spreadsheets Build association logic to companies, contacts, and deals Design opportunity identification workflows and scoring Create playbooks for sales team to update equipment records Develop equipment-based reporting and account insights | Current dragline custom object serves as foundation Client to provide haul truck and shovel databases Focus on technology sales team adoption and usability Includes data import plan but not full execution Recommendations for ongoing data maintenance and updates | 14 | 18 | 16 | FALSE
Now | Optimization Recommendations | ERP Integration Readiness Roadmap | As a sales operations manager, I want a clear roadmap for preparing HubSpot for Infor Syteline Cloud integration so that we maximize the value of both systems and eliminate manual data transfer. | Pre-Integration Data Cleanup Integration Architecture Design Process Alignment | Infor Syteline Cloud timeline confirmed for 2026 Client to provide ERP migration plan and API documentation Integration build separate project following optimization Focus on requirements and readiness during assessment Includes high-level integration architecture diagram | 16 | 20 | 18 | FALSE
Now | Strategic Planning & Roadmap | Prioritized Implementation Roadmap | As a project stakeholder team, we want a clear prioritized roadmap for implementing optimization recommendations so that we can budget appropriately and sequence work for maximum impact. | Phase 1: Foundation & Quick Wins (Pre-ERP Integration) Phase 2: Process Automation & Enhancement (2025 Q4 - 2026 Q1) Phase 3: ERP Integration & Advanced Features (2026) | Roadmap aligned with client budget cycles and ERP timeline Includes effort estimates and cost ranges for each phase Prioritization based on ROI and business impact Flexibility for adjustments based on business changes Change management and training considerations throughout | 12 | 16 | 14 | FALSE
Now | Strategic Planning & Roadmap | Change Management & Adoption Strategy | As a sales operations manager who has experienced multiple leadership changes, I want a change management plan that will drive adoption and sustain improvements regardless of future organizational changes. | Stakeholder Engagement Plan Executive sponsor alignment and communication Regional sales manager buy-in strategy Sales rep training and support approach Service and marketing team onboarding Training & Enablement Role-based training modules (sales, service, operations) Mobile app training for field sales team Admin training for Katie and future team members Create internal documentation and reference guides Adoption Measurement Define success metrics and KPIs Create adoption dashboards and scorecards Design feedback loops and continuous improvement process Plan for regular check-ins and optimization cycles | Includes change management framework and communication templates Training plan outline with recommendations for execution Client responsible for ongoing adoption reinforcement Aptitude 8 can provide training delivery as separate engagement Success metrics defined collaboratively with leadership | 10 | 14 | 12 | FALSE
Now | Presentation | Executive Presentation Preparation | As a strategy consultant, I want to prepare executive presentation so that we effectively communicate findings and recommendations. | Summarize insights, quick wins, long-term plan. | • Includes one executive-ready slide deck. • Excludes additional department-level versions. • Client to confirm final audience. | 4 | 5 | 5 | FALSE
| Implementation Support | Strategy to Delivery Handoff | As a delivery team receiving a completed optimization assessment, we want to conduct a comprehensive handoff session with the strategy team and client stakeholders so that we fully understand the current state challenges, strategic recommendations, prioritized roadmap, and client context needed to successfully execute the implementation project. | Internal Handoff Session (Strategy Team → Delivery Team) Client Transition Call (Strategy Team + Delivery Team + Client) Delivery Team Onboarding | Receive complete strategy assessment documentation including technical audit findings, process discovery notes, and optimization recommendations | 8 | 10 | 9 | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Config
Configuration | Value | Description | HubSpot Property
Gdrvie + Deal Inputs
Company Name | Flanders | Client company name for proposals
Google Folder | https://drive.google.com/drive/folders/1plB3ne9dulMHvuRiGkkuA91iAHs6oM_U | Needs to be manually input for the time being, will be set by the Pipedream automation
Deal Record ID | 45116554907 | HubSpot deal record ID, needs to be manually input for the time being, will be set by the Pipedream automation
Last Sync to HubSpot |  | The last time the story doc was sync'd to the HubSpot deal record
Client Page
Client Page URL | https://script.google.com/macros/s/AKfycbzGfZXXrB8GB7kt-FSeTA8sL0Rw3BzaXwifNA9CDpjsqe8NBn4EL159NLqLBYwGjqUw/exec?sheetId=1Q6S47MCBPBi__7_ddV-STx-yXQL5e5L80MiCRCPIUpQ | The URL of the page that will be shared in Trumpet | customer_stories_client_url
Last Client Page URL Generated | 2025-10-16 10:44 | The last time you created/updated a URL so we can understand deployment app versions
Client Page Status | Final Presentation | Determines page status for the shared link
Project ID | ------ | TBD on usage to facilitate project creation
Solutions Architect |  | SA assigned to this project
Request Scope Review |  | Future-state functionality incoming
Scope Reviewed |  | Future-state functionality incoming
NOW Project
Hourly Project Rate | 325 | Standard hourly rate for most services | project_hourly_rate
Project Management Factor | 20% | Percentage markup for project management
Project Management Content | To support management and communication, a project manager and delivery lead will own all A8 tasks and clearly communicate needs. - Visibility to budget spend will be provided during the duration of the project - A8 will provide check-in agenda items and follow-ups - Flanders to communicate to A8's shared inbox for easier collaboration and timely responses - Flanders driven delay will result in additional PM time billed to manage timeline | Description text for the PM section. editable by you.
SA Expected Start Date | 2025-10-06 | Project start date
Total Project Months | 3 | Expected project duration | project_duration
NEXT Support Retainer
Post-Launch Hourly Rate |  | Post-launch rate, a zero here will hide the workstream/section | retainer_hourly_rate
Post-Launch Hours Per Month |  | Post-launch hours per month, a zero here will hide the workstream/section | retainer_hours_per_month_sold
Post-Launch # of Months |  | Post-launch months, a zero here will hide the workstream/section | retainer_months_sold
Post-Launch Support Content | Hours dedicated to post go-live support. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.) | Description text for the post-launch section
Additional Notes + Considerations
Additional Notes | - The assumptions content in this scope is based on information and discovery during the sales evaluation and is subject to change during the project if additional challenges or barriers are discovered. - A8 is a Time & Materials agency, we will provide transparent budget tracking throughout the project and change orders will require approvals. - We interchange between A8 and Aptitude 8 in this document. | Description text for below the investment summaries, but above the later phase workstreams

## Calculations
HubSpot Property
Calculated Project Details
Total Service Hours Hours | 196 | Total amount of Input rows
Total Project Management Hours | 39 | Based on PM % in Config Sheet
Total Project Hours Sold | 235 | Service + PM | project_hours_sold
Total Retainer Hours Sold | 0
Total Engagement Hours Sold | 235 | This should match exactly to the investment block on the HTML Page | sold_hours
Deal Amount | 76375 | This should match exactly to the investment block on the HTML Page | amount
Expected End Date | 2026-01-06
Expected Project Hours/Month | 66
Linear Expected Project Hours/Week | 16
Peak Project Expected Hours/Week | 19.2
Low Project Expected Hours/Week | 8
Dev Work Percentage | 12.5% |  | dev_work_pct
SE Work Percentage | 0% |  | se_work_pct
Calculated Function Summary
| Sum of Hours | Percent of
Consulting | 10 | 17.86%
Development | 7 | 12.5%
Project Management | 39 | 69.64%
Solutions Engineering | 0 | 0%
Strategy | 0 | 0%
Sum of Function-Based Hours | 56 | 100%
Calculated Ranges | Low Hours | High Hours
Project Service Estimates: | 167 | 221
Project Management: | 33 | 44
Post-Project Support: | 0 | 0
Hour Estimates: | 200 | 265
Investment Ranges: | 65000 | 86125
SOW Summarized Line Items
Workstream | Total Hours | Total Investment
Mobilization | 10 | 3250
Optimization Recommendations | 74 | 24050
Presentation | 5 | 1625
Process Discovery & Documentation | 25 | 8125
Reporting & Analytics Strategy | 24 | 7800
Strategic Planning & Roadmap | 26 | 8450
Technical Assessment | 32 | 10400
Project Management | 39 | 12675
Post-Launch Support | 0 | 0