## User Stories
Epic Name | Epic Description | User Story Title | User Story | Acceptance Criteria | Next Steps | Priority | Effort Level | High Hours Estimate
Sales Team Enablement with Freshsales | Transform manual sales processes into an intelligent Freshsales-powered sales platform that maximizes conversion rates and agent productivity while integrating with existing Freshdesk operations | Intelligent Lead Scoring in Freshsales | As a sales agent, I want Freshsales to automatically score and rank my prospects based on our historical data so that I can focus my time on the highest-value opportunities first | Lead scoring considers inquiry type, domain authority, and past spending patterns; Leads are automatically prioritized in Freshsales dashboards; Scoring factors are configurable and transparent to sales agents | 1. Define scoring criteria for Freshsales 2. Map data sources from Freshdesk 3. Build Freshsales scoring model 4. Create agent dashboard views | Phase 1 | Medium | 20
Sales Team Enablement with Freshsales | Transform manual sales processes into an intelligent Freshsales-powered sales platform that maximizes conversion rates and agent productivity while integrating with existing Freshdesk operations | Unified Customer Intelligence Across Platforms | As a sales agent, I want Freshsales to display complete customer profiles with order history from Zoho so that I can provide personalized service and identify cross-sell opportunities | Zoho Books/Invoice ↔ Freshsales -Automatic invoice creation when deals close in Freshsales -Customer data synchronization -Payment status updates flow back to Freshsales -Revenue recognition automation | Option 1. Zoho Flow (Zapier-like automation) -Visual workflow builder to connect Freshsales with any Zoho product -Trigger-based automations (e.g., deal closed → create invoice) -Multi-step workflows with conditional logic Option 2. APIs -Both Freshsales and Zoho products have robust REST APIs -Custom integrations possible for complex requirements -Webhook support for real-time data sync | Phase 1 | Large | 40
Sales Team Enablement with Freshsales | Transform manual sales processes into an intelligent Freshsales-powered sales platform that maximizes conversion rates and agent productivity while integrating with existing Freshdesk operations | Deal Pipeline Automation with Freshdesk Integration | As a sales manager, I want Freshsales to automatically track deals and forecast revenue while syncing order fulfillment status from Freshdesk so that I can predict revenue without manual reporting | Automated deal tracking in Freshsales from initial contact to payment; Revenue forecasting based on historical conversion rates from our data; Integration with Freshdesk shows order fulfillment and publishing status; Automated stage progression when orders are marked complete in Freshdesk; Dashboard shows bottlenecks in both sales and fulfillment processes | 1. Configure Freshsales deal pipeline stages 2. Build Freshdesk integration for order status 3. Import historical conversion data 4. Create forecasting algorithms 5. Build management dashboard | Phase 1 | Large | 30
Cross-Platform Communication Excellence | Ensure seamless customer communication and experience across Freshsales and Freshdesk platforms while maintaining brand consistency | Seamless Handoff from Sales to Support | As a customer, I want a smooth transition from the sales process in Freshsales to order fulfillment in Freshdesk so that I don't have to repeat information or lose communication continuity | Automatic customer record creation in Freshdesk when a deal hits the 'Order Confirmed' Stage in Freshsales; All sales communication history transfers to Freshdesk support ticket; Customer contact information syncs accurately between platforms; Order details and special requirements transfer automatically; Single customer ID links records across both systems | 1. Design customer handoff workflow 2. Build Freshsales to Freshdesk automation 3. Create data mapping for customer transfer 4. Implement communication history sync 5. Test handoff scenarios | Phase 1 | Medium | 15
Cross-Platform Communication Excellence | Ensure seamless customer communication and experience across Freshsales and Freshdesk platforms while maintaining brand consistency | Brand-Consistent Communication | As a customer, I want to receive sales communications from Freshsales using the same domain I originally contacted so that I have confidence I'm dealing with the legitimate business | Freshsales configured to send emails from appropriate domain (e.g. contact@betterthisworld.com); Email signatures and branding consistent between sales and support; Domain authentication properly configured for deliverability; Customer can reply to sales emails and responses route to correct sales agent; Integration maintains domain-specific routing for our 5000+ websites | 1. Configure domain authentication in Freshsales 2. Set up email routing for 5000+ domains 3. Create consistent branding templates 4. Test email deliverability 5. Implement reply routing logic | Phase 1 | Large | 30
Cross-Platform Communication Excellence | Ensure seamless customer communication and experience across Freshsales and Freshdesk platforms while maintaining brand consistency | Unified Communication Threading | As a sales agent, I want Freshsales to maintain conversation continuity with prospects while allowing support handoff to Freshdesk so that customers don't lose communication context | All sales communication in single thread within Freshsales; Communication history accessible to support team when creating Freshdesk tickets; Automatic notification when support ticket is created for sales prospect; Ability to CC or notify sales agent on critical support communications; Conversation context preserved during platform handoff | 1. Design conversation threading in Freshsales 2. Build communication history transfer 3. Create notification system between platforms 4. Implement context preservation 5. Test communication flows | Phase 2 | Large | 13
Automated Sales Operations | Streamline and automate sales operations to reduce manual work and improve efficiency across the sales process | Intelligent Lead Routing from Freshdesk to Freshsales | As a sales manager, I want prospects identified in Freshdesk to be automatically created as leads in Freshsales so that no sales opportunities are missed in our support queue | AI analysis of Freshdesk tickets identifies sales opportunities; Automatic lead creation in Freshsales for sales-related inquiries; Proper attribution to correct sales agent based on website/domain; Duplicate prevention for existing customers/prospects; Escalation rules for high-value prospects | 1. Build AI analysis for Freshdesk tickets 2. Create lead identification logic 3. Build Freshdesk to Freshsales lead creation 4. Implement agent assignment rules 5. Add duplicate prevention | Phase 1 | Large | 20
Automated Sales Operations | Streamline and automate sales operations to reduce manual work and improve efficiency across the sales process | Automated Quote Generation | As a sales agent, I want Freshsales to generate the first 2 communications (Pricing and Discount) automatically based on our pricing content so that I can respond to prospects quickly and consistently | Use the Pricing and Discount workflows and content from Freshdesk in Freshsales | 1. Build email templates for each communication 2. Create workflows | Phase 1 | Medium | 15
Automated Sales Operations | Streamline and automate sales operations to reduce manual work and improve efficiency across the sales process | Revenue Recognition Integration | As a finance team member, I want Freshsales to automatically trigger invoice creation in Zoho when ticket has moved to the 'Send Invoice' stage so that revenue recognition is immediate and accurate | Automatic integration with Zoho billing; Ticket moving to 'Send Invoice' in Freshdesk triggers invoice generation; Proper revenue recognition for both PMP and Kojak business units; Integration with our order fulfillment tracking; Financial reporting shows sales attribution and conversion metrics | 1. Build Freshsales to Zoho billing integration (done in previous story) 2. Configure 'Send Invoice' triggers 3. Create financial reporting | Phase 1 | Medium | 10
Analytics and Reporting | Provide comprehensive analytics and reporting capabilities that leverage data from both Freshsales and existing systems | Sales Performance Dashboard | As a sales manager, I want Freshsales dashboards that show individual and team performance with data from our website portfolio so that I can identify coaching opportunities and optimize territory assignments | Individual agent performance metrics in Freshsales; Territory performance based on website portfolio data; Conversion rates by domain category and authority level; Coaching recommendations based on performance patterns | 1. Design performance dashboard layout 2. Create performance metrics calculations 3. Implement coaching recommendation logic 4. Build territory optimization tools | Phase 2 | Medium | 20
Analytics and Reporting | Provide comprehensive analytics and reporting capabilities that leverage data from both Freshsales and existing systems | Predictive Revenue Forecasting | As a business owner, I want a BI tool to provide predictive analytics using our 5-year customer database so that I can plan resources and investments confidently | Revenue forecasting based on historical conversion patterns; Seasonal trend analysis from our extensive customer database; Pipeline health scoring and risk assessment; Integration with website performance data for market insights; Scenario planning for different growth strategies | 1. Import 5-year historical customer data into selected BI tool 2. Build predictive analytics models 3. Create seasonal trend analysis | Phase 2 | Large | 80
Analytics and Reporting | Provide comprehensive analytics and reporting capabilities that leverage data from both Freshsales and existing systems | Cross-Platform Customer Journey Analytics | As a business analyst, I want to track complete customer journeys from initial Freshsales contact through Freshdesk fulfillment so that I can optimize our entire customer experience | Complete customer journey mapping across both platforms; Time-to-close and time-to-fulfill metrics; Bottleneck identification in sales and fulfillment processes; Customer satisfaction correlation with sales experience; ROI analysis for sales efforts by domain and customer segment | 1. Design customer journey tracking 2. Build cross-platform analytics 3. Create bottleneck identification tools 4. Implement satisfaction correlation analysis 5. Build ROI reporting | Phase 2 | Large | 13
Data Integration and Consistency | Ensure consistent and synchronized data across all platforms while maintaining data integrity and performance | Master Customer Data Management | As a data analyst, I want synchronized customer data between Freshsales and Freshdesk so that we have consistent customer information regardless of which platform team members are using | Real-time bidirectional sync between Freshsales and Freshdesk; Master customer record maintained with all interaction history; Conflict resolution for data discrepancies; Customer entity resolution across multiple email addresses; Integration with our Snowflake data warehouse | 1. Design master data model 2. Build bidirectional sync mechanism 3. Implement conflict resolution logic 4. Create entity resolution system 5. Integrate with Snowflake --- 1. Customer Master Data (Bidirectional) - Universal customer ID, contact info, company details - Prevents data inconsistencies between platforms - Handles challenge of customers using multiple emails 2. Communication History (Bidirectional) - All emails, calls, notes visible in both platforms - Maintains conversation continuity during handoffs - Critical for customer service quality 3. Deal → Order Handoff (Event-driven) When deal hits 'Order Confirmed' in Freshsales → Creates order in Freshdesk Transfers all context: pricing, requirements, customer notes Automates their current manual process 4. Order Status Updates (Freshdesk → Freshsales) - Publishing status, completion dates, live URLs - Revenue recognition triggers - Sales agent notifications | Phase 1 | Large | 40
Data Integration and Consistency | Ensure consistent and synchronized data across all platforms while maintaining data integrity and performance | Business Unit Separation with Cross-Selling | As a business manager, I want Freshsales to maintain separation between PMP and Kojak data while enabling cross-selling opportunities so that each business unit operates independently but leverages our complete database | Clear business unit separation in Freshsales data structure; Cross-selling recommendations when appropriate; Separate pricing and commission structures; Independent reporting by business unit; Shared customer intelligence for strategic accounts | 1. Design business unit data structure 2. Build cross-selling recommendation engine 3. Implement separate pricing systems 4. Create independent reporting 5. Build strategic account sharing | Phase 2 | Medium | 15
Scale and Growth Support | Support the company's rapid growth and scaling requirements while maintaining system performance and operational efficiency | Multi-Domain Sales Management | As a sales director, I want Freshsales to handle our portfolio of 5000+ domains with appropriate scaling and performance so that system performance doesn't degrade as we continue growing our portfolio | Freshsales performance optimized for large domain portfolios; Efficient data structure for website-based sales territories; Automated domain onboarding process; Bulk operations for portfolio management; Integration with our automated website creation process | 1. Optimize Freshsales for large portfolios 2. Design efficient territory structure 3. Build automated domain onboarding 4. Create bulk management tools 5. Integrate with website creation process | Phase 1 | Large | 20
Sales Sequences and Nurture Campaigns | Implement automated sales sequences and nurture campaigns to maximize lead conversion and maintain engagement throughout the customer journey | Automated Sales Sequences | As a sales agent, I want Freshsales to automatically follow up with prospects using personalized sequences based on their domain type and engagement level so that I can maintain consistent contact without manual tracking | Automated email sequences trigger based on lead behavior and domain authority; Personalized content based on website performance data from Ahrefs; Sequence customization by business unit (PMP vs Kojak); Automatic pause when prospect responds or engages; Integration with our domain portfolio for relevant examples | 1. Design sequence templates by domain type 3. Create behavioral triggers 4. Implement pause/resume logic 5. Build performance tracking | Phase 2 | Large | 20
Sales Sequences and Nurture Campaigns | Implement automated sales sequences and nurture campaigns to maximize lead conversion and maintain engagement throughout the customer journey | Re-engagement Campaigns for Dormant Customers | As a customer success manager, I want automated re-engagement sequences for customers who haven't ordered in 90+ days using data from their previous orders so that we can recover lost revenue and identify why they stopped buying | Automatic identification of dormant customers from Freshdesk order history; Personalized re-engagement based on their previous service types and domains; Special offers or incentives for returning customers; Integration with their historical performance data; Win-back campaign tracking and success measurement | 1. Build dormant customer identification logic 2. Create personalized win-back templates 3. Design incentive structure 4. Integrate historical order data 5. Build campaign performance tracking 6. Implement automatic deployment | Phase 3 | Medium | 15
Sales Sequences and Nurture Campaigns | Implement automated sales sequences and nurture campaigns to maximize lead conversion and maintain engagement throughout the customer journey | Cross-Selling Sequence Automation | As a sales manager, I want automated sequences that identify and pursue cross-selling opportunities between PMP and Kojak services based on customer behavior and domain portfolio so that we maximize revenue per customer | Automatic identification of cross-sell opportunities based on customer's current domain authority; Sequences for upselling from Kojak (tier 2) to PMP (tier 1) services; Down-sell sequences for budget-conscious PMP customers to Kojak options; Integration with customer purchase history and domain performance data; Revenue impact tracking for cross-sell success | 1. Build cross-sell opportunity detection 2. Create tier-specific sequence templates 3. Integrate domain authority data 4. Design upsell/downsell logic 5. Implement revenue tracking | Phase 2 | Large | 10
Sales Sequences and Nurture Campaigns | Implement automated sales sequences and nurture campaigns to maximize lead conversion and maintain engagement throughout the customer journey | Sequence Performance Analytics | As a sales manager, I want detailed analytics on sequence performance including open rates conversion rates and revenue attribution so that I can optimize our automated outreach and improve conversion rates | Comprehensive sequence performance dashboards in Freshsales; A/B testing capabilities for sequence variations; Revenue attribution from sequences to closed deals; Performance comparison across different domain types and customer segments; Recommendations for sequence optimization based on data | 1. Build sequence analytics dashboard 2. Implement A/B testing framework 3. Create revenue attribution tracking 4. Build segment performance comparison 5. Develop optimization recommendations engine | Phase 2 | Medium | 15
Freshdesk Service Operations | Acceptance Criteria | Publishing Support Ticket Routing | As a customer, I want my publishing-related issues automatically routed to the publishing team so that I get expert help with content problems | When I submit a ticket about content, SEO, or website issues, it's automatically assigned to the publishing team; I receive confirmation that my issue has been routed to the appropriate specialist; Publishing team receives tickets with relevant context and customer history; Routing happens within 5 minutes of ticket creation | 1. Define publishing issue categories 2. Build routing automation 3. Create publishing team queues 4. Integrate with publishing workflow | Phase 1 | Medium | 15
Freshdesk Service Operations | Publishing issues automatically categorized and routed; Publishing team has dedicated queue; SLA tracking for publishing issues; Integration with Airtable publishing system | Financial Support Automation | As a finance team member, I want payment and billing inquiries automatically categorized and prioritized so that I can resolve financial issues efficiently | Payment-related tickets are automatically tagged with issue type (dispute, overdue, refund, etc.); High-value or urgent financial issues are prioritized in my queue; I can filter my dashboard by financial issue type; System identifies customers with payment history for context | 1. Map financial issue categories and priority rules 2. Create automated tagging workflows based on content analysis 3. Build finance team dashboard views 4. Integrate with Zoho billing data for context | Phase 1 | Large | 18
Freshdesk Service Operations | Payment inquiries auto-categorized; Integration with Zoho for account lookup; Automated response templates for common billing questions; Escalation rules for complex financial issues | Content Issue Classification | As a publishing manager, I want automatic classification of content issues so that I can prioritize fixes based on urgency and type | Content issues are automatically categorized (plagiarism, formatting, broken links, etc.) Issues are assigned urgency levels based on customer tier and SLA I can view dashboard showing issue distribution and team workload Escalation triggers activate for high-priority issues | 1. Define content issue taxonomy and urgency matrix 2. Build GPT-powered classification workflows 3. Create publishing manager dashboard 4. Set up escalation and notification rules | Phase 2 | Large | 13
Freshdesk Service Operations | AI-powered classification of content issues; Priority scoring based on customer value and issue type; Automated assignment to appropriate specialist; SLA tracking by issue complexity | Customer Context Integration | As a publishing team member, I want Freshdesk tickets to automatically update when I complete publishing tasks so that customers are notified without manual intervention | When I mark content as published in our system, customer ticket updates automatically Customer receives notification with live link and publication details Ticket moves to "awaiting invoice" status automatically Publishing completion triggers finance team notification | 1. Map publishing workflow touchpoints for automation 2. Build webhook integrations between publishing tools and Freshdesk 3. Create automated customer notification templates 4. Test end-to-end publishing-to-billing workflow | Phase 1 | Medium | 15
Freshdesk Service Operations | Airtable integration for publishing status; Automatic ticket updates when content goes live; Customer notification automation; Publishing milestone tracking | Publishing Workflow Integration | As a support manager, I want automatic escalation of unresolved issues to appropriate managers so that customer problems don't fall through cracks | Issues unresolved after SLA timeframe automatically escalate to managers Escalation includes full context, customer history, and attempted resolutions I receive escalated issues with clear priority and next steps System tracks escalation patterns for process improvement | 1. Define escalation triggers and timeframes by issue type 2. Create manager notification workflows 3. Build escalation tracking and reporting 4. Configure manager queue views and priorities | Phase 1 | Medium | 10
Freshdesk Service Operations | Time-based escalation rules; Manager notification system; Customer value-based priority adjustment; Executive escalation for VIP customers | Self-Service Portal Enhancement | As a support manager, I want comprehensive analytics on team performance and issue resolution so that I can optimize support operations | Dashboard shows key metrics: resolution time, customer satisfaction, issue volume I can view performance data by team member, issue type, and time period System identifies bottlenecks and improvement opportunities Reports are automatically generated and shared with stakeholders | 1. Define KPIs and reporting requirements 2. Build Freshdesk dashboards and reports 3. Set up automated report distribution 4. Create performance improvement workflows | Phase 2 | Large | 20
Freshdesk Service Operations | Team performance dashboards; Issue resolution time tracking; Customer satisfaction scoring; Trend analysis and improvement recommendations | Escalation Management | As a support agent, I want intelligent automated responses for common inquiries so that I can focus on complex issues requiring human intervention | Common pricing and process questions receive immediate automated responses System identifies when human intervention is needed and routes accordingly I can review and approve automated responses before sending Automated responses include personalized customer context | 1. Analyze current Make.com automation and improve GPT prompts 2. Build Freshdesk workflow with AI-powered response generation 3. Create approval and override mechanisms for agents 4. Monitor response quality and customer satisfaction | Phase 2 | Large | 13
Freshdesk Service Operations | AI-powered response generation; Common issue resolution automation; Automated status updates; Smart routing based on inquiry complexity | Multi-Language Support | As a finance team member, I want a structured process for handling invoice disputes so that I can resolve financial conflicts efficiently | Dispute tickets follow standardized workflow with required information collection I can track dispute status and history in centralized dashboard System provides context about customer payment history and dispute patterns Resolution communications are templated and trackable | 1. Design dispute resolution workflow and required fields 2. Create finance team dispute dashboard 3. Build automated dispute tracking and notifications 4. Integrate with Zoho billing for payment context | Phase 2 | Medium | 20
Freshdesk Service Operations | Dispute categorization and tracking; Automated evidence collection; Manager approval workflows; Resolution documentation and reporting | Performance Analytics | As a finance team member, I want automated collections support for overdue accounts so that I can recover payments systematically | Overdue accounts trigger automated payment reminder sequences I can customize reminder timing and messaging by customer segment System tracks payment recovery success rates and adjusts approaches Manual intervention points are clearly defined and triggered | 1. Design payment reminder sequence and triggers 2. Build automated collections workflows in Freshdesk 3. Create collections tracking dashboard 4. Integrate with payment systems for real-time status updates | Phase 2 | Medium | 10
Freshdesk Service Operations | Overdue account identification; Automated payment reminder sequences; Collections workflow management; Legal escalation procedures | Automated Response System | As a support agent, I want to see complete customer interaction history so that I can provide contextual support without repeating questions | Customer record shows all previous tickets, orders, and interactions I can see customer's website portfolio and recent publishing activity Payment history and account status are visible in sidebar Related tickets and similar issues are suggested automatically | 1. Design comprehensive customer record layout 2. Integrate all data sources (orders, payments, publishing, support) 3. Build intelligent suggestion engine for related issues 4. Create agent training materials for new interface | Phase 1 | Large | 8
Integration with HubSpot for sales history; Email thread consolidation; Interaction timeline visualization; Cross-system activity tracking

## Lead Scoring
Category | Criteria | Points | Threshold/Condition | Notes
Customer Profile | Repeat customer (existing in system) | 25 | Found in CRM database | Highest priority indicator
Customer Profile | Agency/Platform (multiple domains) | 20 | Business email domain or multiple requests | Indicates bulk potential
Customer Profile | Business email domain | 15 | Non-Gmail/Yahoo domain | Professional buyer indicator
Customer Profile | Gmail/Yahoo personal email | 5 | Personal email domains | Lower priority but valid
Customer Profile | Suspicious/temp email | -10 | Temporary or suspicious domains | Likely spam
Order Characteristics | Bulk order (5+ articles) | 20 | 5 or more articles requested | High-value transaction
Order Characteristics | High-value site requested (DR70+) | 15 | Tier 1 site in request | Quality-conscious buyer
Order Characteristics | Specific article provided | 10 | Content ready to publish | Serious intent
Order Characteristics | Just asking for pricing | 5 | General pricing inquiry | Standard lead
Order Characteristics | Vague/unclear request | -5 | Unclear requirements | Time waster indicator
Timing & Behavior | Response within 1 hour | 15 | Fast response to auto-reply | High engagement
Timing & Behavior | Business hours contact | 10 | 9 AM - 6 PM local time | Professional behavior
Timing & Behavior | Professional language/tone | 10 | Proper grammar and tone | Serious buyer
Timing & Behavior | Weekend/off-hours contact | 5 | Outside business hours | Standard timing
Timing & Behavior | Poor grammar/unprofessional | -5 | Bad grammar or tone | Quality concern
Market Indicators | Tier 1 target site requested | 10 | Premium site mentioned | Sophisticated buyer
Market Indicators | Mentioned budget/pricing | 8 | Budget discussion included | Ready to purchase
Market Indicators | Competitive research evident | 5 | Knows market pricing | Informed buyer
Market Indicators | SEO knowledge demonstrated | 5 | Industry terminology used | Expert customer
Market Indicators | Mass/template outreach signs | -5 | Generic template message | Low-quality lead
Score Range | Lead Type
80-100 | Hot Lead
50-79 | Warm Lead
20-49 | Cold Lead
0-19 | Low Quality
Example Scenarios | Customer Type | Order Details | Behavior | Final Score | Lead Type
Returning Agency | Business email, repeat customer (+45) | Bulk order, 10 articles, high-DR sites (+35) | Professional, business hours (+25) | 105 (capped at 100) | Hot Lead
New Professional | Business domain (+15) | Single high-value site, content ready (+25) | Professional tone, specific needs (+20) | 60 | Warm Lead
First-time Buyer | Gmail address (+5) | Single article request (+10) | Good grammar, business hours (+15) | 30 | Cold Lead
Mass Outreach | Suspicious email (-10) | Vague request (-5) | Template message, poor grammar (-10) | -25 (floor at 0) | Low Quality

## Sales Pipeline
Stage ID | Stage Name | Entry Trigger | Target Duration | Agent Action | Exit Criteria | Agent SLA | Deal Value Stage
1 | New | Website form submission or email inquiry | 0-2 hours | Initial response and lead qualification | Agent responds and qualifies the inquiry | 1 hour response | Prospecting
2 | Negotiation | Confirmed legitimate inquiry with specific needs | 2-24 hours | Provide pricing, site metrics, answer questions | Customer shows purchase intent or requests specific sites | Same day proposal | Qualification
3 | Price Argeed On | Customer agrees on pricing | 1-3 days | Custom proposal with specific sites and pricing | Customer approves proposal and provides content | 2 follow-ups max | Proposal
4 | Order Confirmed | Customer provides article/content for publishing | 1-4 hours | Review content, confirm publishing timeline | Content approved and sent to publishing team | Monitor progress | Negotiation
5 | Paid | Payment confirmed from Zoho | Immediate | Thank customer, suggest additional opportunities | Transaction complete | Same day acknowledgment | Closed Won
6 | Closed Lost - Not Qualified | Determined to be spam, low-quality, or not legitimate | Immediate | Minimal response or no response | Marked as unqualified | No response required | Closed Lost
| Closed Lost - No Response | No response after 3 follow-ups | After 7 days | Move to long-term nurture sequence | Transferred to marketing | Transfer within 24h | Closed Lost
| Closed Lost - Content Rejected | Content fails quality/plagiarism checks repeatedly | After 3 attempts | Explain requirements, offer second chance | Customer provides acceptable content or abandons | Final response within 24h | Closed Lost
| Closed Lost - Non-Payment | No payment after 7 business days | After 7 days | Remove content, send final notice | Content removed, collections initiated | Remove content same day | Closed Lost
Dashboard Views | Role | Primary Metrics | Refresh Rate | Access Level
Agent Dashboard | Sales Agent | My active deals, overdue follow-ups, daily targets, commission tracking | Real-time | Individual agent data only
Team Lead Dashboard | Team Manager | Team performance, conversion rates, agent productivity, bottleneck identification | Every 15 minutes | Full team visibility
Executive Dashboard | C-Level | Revenue forecasting, pipeline health, market trends, ROI analysis | Every hour | Company-wide access
Operations Dashboard | Operations Manager | Publishing queues, quality metrics, SLA compliance, resource allocation | Real-time | Cross-functional visibility
Finance Dashboard | Finance Team | Payment tracking, collections, revenue recognition, late fees | Every hour | Financial data access
Customer Success Dashboard | Account Managers | Customer satisfaction, retention rates, upsell opportunities | Daily | Customer relationship data