## Input
Display | Workstream | Service_Title | Customer_Story | Suggested_Path | Assumptions | Estimated_Low_Hours | Estimated_High_Hours | Contracted_Hours | Requires_Clarification | Function | Library_ID | Project_ID | Internal_Notes | Task_Link
Now | Mobilization | Engagement Mobilization & Kickoff Prep | The client seeks to simplify a highly customized HubSpot–Firebase–Stripe ecosystem, rationalize membership data structures, and evaluate whether the member hub can be rebuilt natively in HubSpot ahead of the 2026 event cycle. | Review Intro + Reverse Demo recordings, PRD, and legacy diagrams; confirm engagement objectives; define stakeholder map and interview plan; develop Discovery agenda and data-access checklist. | - Includes 2 internal planning sessions and 1 client alignment call. - Client provides system access, org chart, and PRD prior to kickoff. - Strategy only—no build or cleanup. - Change requests beyond defined stakeholders trigger scope amendment. | 2 | 3 | 3 | FALSE | Strategy |  |  | - One row per business process - 2 meetings for low complexity, 3-4 meetings for moderate complexity, 5+ for high complexity projects
Now | Discovery | Executive & Overview Interview | Leadership seeks to simplify operations before renewal and validate direction toward a HubSpot-native member hub. | Conduct interview with Head of Technology to define strategic success criteria and constraints. | - 1 hr prep, 1 hr conduct, 1 hr summary. - Up to 3 A8 attendees. - Limited to overview - not technical deep dive. - Additional exec sessions billed separately. | 2 | 3 | 3 | FALSE | Strategy
Now | Discovery | Event Operations Interview | Event content (speakers, schedule, exhibitors) is managed in multiple systems (Sanity, Firebase, HubSpot). | Interview event team to define event-data lifecycle: content creation, publishing, sync to mobile/web; identify MVP elements for the 2026 event app. | - 1 hr prep/conduct/summary.- Advisory only. - Event app build excluded. - MVP feature set aligned with PRD §9. | 2 | 4 | 3 | FALSE | Strategy
Now | Discovery | Technology Interview | The organization’s tech stack includes HubSpot, Firebase, Sanity, Stripe, and QuickBooks, with active simplification efforts underway. | Interview technology and RevOps team to validate architecture assumptions and platform dependencies; identify pain points in sync logic, error handling, and API usage. | - 1 hr prep/conduct/summary - One additional hr for extra A8 attendee. - Focus on conceptual system design only. - Access limited to architecture review, not code. | 2 | 4 | 3 | FALSE | Solutions Engineering
Now | Technical Analysis | Integration & Architecture Review | The legacy React/Firebase app syncs daily with HubSpot and handles profile data, membership years, and event content; payments logic runs across HubSpot, Stripe, and QuickBooks. | Map data flow between systems; review Firebase, HubDB, and Stripe touchpoints; define system boundaries; identify opportunities to centralize data within HubSpot and reduce sync volume. | - Includes 1 working session with Head of Technology. - Limited to architecture documentation and recommendations. - API call and webhook limits analyzed conceptually only. - Future integration builds excluded. | 5 | 8 | 7 | FALSE | Solutions Engineering |  |  | - At least one 60 minute meeting for low complexity, at least two 60 minute meetings for moderate complexity, and at least 3 for high complexity projects
Now | Analysis | Data & Process Gap Analysis | System contains legacy workflows, inconsistent object use, and unclear ownership of membership data. | Compare current vs. desired state across data, process, and roles; identify redundancies, missing controls, and dependency risks; summarize in findings deck. | - Includes 1 internal review cycle. - Gaps prioritized by business impact. - Implementation recommendations remain high-level. - No data remediation. | 3 | 5 | 4 | FALSE | Solutions Engineering |  |  | We MUST link to a record count table: https://docs.google.com/spreadsheets/d/18OdVki4GwB7b5KkIuucGZQFz7VyOZaNvvpfWpufauPk/edit?gid=1360770003#gid=1360770003
Now | Planning & Roadmap | Risk & Dependency Planning | Platform renewal, data hygiene, and event deadlines present major dependencies. | Document risk register and dependency matrix; outline mitigation plans for renewal, data cleanup, and system access. | - Includes 1 review cycle with client. - Risk scoring qualitative only. - Separate risk logs maintained by client post-engagement. - Strategic scope only. | 3 | 5 | 4 | FALSE | Strategy
Now | Documentation | Findings Readout | Leadership requires an executive summary of discovery and assessment results. | Prepare and deliver findings presentation summarizing pain points, data architecture, and gap analysis outcomes. | - Includes draft + final. - 60–90 min delivery. - One revision cycle. - No redesign after approval. | 3 | 5 | 4 | FALSE | Strategy
FALSE
|  |  |  | Low Hours Estimate | 26 |  |  |  | FALSE
|  |  |  | High Hours Estimate | 44 |  |  |  | FALSE
|  |  |  | Total Estimated Engagement Hours | 37 |  |  |  | FALSE
|  |  |  | Total Estimated Investment | 12025 |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## ClickUp Import
Task Type | Task Name | Description Content | High Hours Estimate | Contracted Hours
Workstream | Analysis
Customer Story | Data & Process Gap Analysis | System contains legacy workflows, inconsistent object use, and unclear ownership of membership data. Compare current vs. desired state across data, process, and roles; identify redundancies, missing controls, and dependency risks; summarize in findings deck. - Includes 1 internal review cycle. - Gaps prioritized by business impact. - Implementation recommendations remain high-level. - No data remediation. | 5 | 4
Workstream | Discovery
Customer Story | Executive & Overview Interview | Leadership seeks to simplify operations before renewal and validate direction toward a HubSpot-native member hub. Conduct interview with Head of Technology to define strategic success criteria and constraints. - 1 hr prep, 1 hr conduct, 1 hr summary. - Up to 3 A8 attendees. - Limited to overview - not technical deep dive. - Additional exec sessions billed separately. | 3 | 3
Customer Story | Event Operations Interview | Event content (speakers, schedule, exhibitors) is managed in multiple systems (Sanity, Firebase, HubSpot). Interview event team to define event-data lifecycle: content creation, publishing, sync to mobile/web; identify MVP elements for the 2026 event app. - 1 hr prep/conduct/summary.- Advisory only. - Event app build excluded. - MVP feature set aligned with PRD §9. | 4 | 3
Customer Story | Technology Interview | The organization’s tech stack includes HubSpot, Firebase, Sanity, Stripe, and QuickBooks, with active simplification efforts underway. Interview technology and RevOps team to validate architecture assumptions and platform dependencies; identify pain points in sync logic, error handling, and API usage. - 1 hr prep/conduct/summary - One additional hr for extra A8 attendee. - Focus on conceptual system design only. - Access limited to architecture review, not code. | 4 | 3
Workstream | Documentation
Customer Story | Findings Readout | Leadership requires an executive summary of discovery and assessment results. Prepare and deliver findings presentation summarizing pain points, data architecture, and gap analysis outcomes. - Includes draft + final. - 60–90 min delivery. - One revision cycle. - No redesign after approval. | 5 | 4
Workstream | Mobilization
Customer Story | Engagement Mobilization & Kickoff Prep | The client seeks to simplify a highly customized HubSpot–Firebase–Stripe ecosystem, rationalize membership data structures, and evaluate whether the member hub can be rebuilt natively in HubSpot ahead of the 2026 event cycle. Review Intro + Reverse Demo recordings, PRD, and legacy diagrams; confirm engagement objectives; define stakeholder map and interview plan; develop Discovery agenda and data-access checklist. - Includes 2 internal planning sessions and 1 client alignment call. - Client provides system access, org chart, and PRD prior to kickoff. - Strategy only—no build or cleanup. - Change requests beyond defined stakeholders trigger scope amendment. | 3 | 3
Workstream | Planning & Roadmap
Customer Story | Risk & Dependency Planning | Platform renewal, data hygiene, and event deadlines present major dependencies. Document risk register and dependency matrix; outline mitigation plans for renewal, data cleanup, and system access. - Includes 1 review cycle with client. - Risk scoring qualitative only. - Separate risk logs maintained by client post-engagement. - Strategic scope only. | 5 | 4
Workstream | Technical Analysis
Customer Story | Integration & Architecture Review | The legacy React/Firebase app syncs daily with HubSpot and handles profile data, membership years, and event content; payments logic runs across HubSpot, Stripe, and QuickBooks. Map data flow between systems; review Firebase, HubDB, and Stripe touchpoints; define system boundaries; identify opportunities to centralize data within HubSpot and reduce sync volume. - Includes 1 working session with Head of Technology. - Limited to architecture documentation and recommendations. - API call and webhook limits analyzed conceptually only. - Future integration builds excluded. | 8 | 7
Workstream | Project Management |  |  | 6
Customer Story | Project Kickoff, Onboarding, and Closeout
Customer Story | Recurring Project Check-ins
Customer Story | Project Administration

## Config
Configuration | Value | Description | HubSpot Property
GDrive + Deal Inputs
Company Name | Abundance 360 | Client company name for proposals
Google Folder |  | Needs to be manually input for the time being, will be set by the Pipedream automation
Deal Record ID | 47091403545 | HubSpot deal record ID, needs to be manually input for the time being, will be set by the Pipedream automation
Last Sync to HubSpot | 2025-11-14 12:02 | The last time the story doc was sync'd to the HubSpot deal record
Solutions Architect |  | SA assigned to this project
Scoping Status | Scope Confirmation |  | scoping_status
Project ID | ------ | TBD on usage to facilitate project creation
Client HTML Page
Client Page URL | https://script.google.com/macros/s/AKfycbzGfZXXrB8GB7kt-FSeTA8sL0Rw3BzaXwifNA9CDpjsqe8NBn4EL159NLqLBYwGjqUw/exec?sheetId=1XSkondMCo7z5jowNhEbeZgN7K9maiCcNMXQDZEgV47s | The URL of the page that will be shared in Trumpet | customer_stories_client_url
Last Client Page URL Generated | 2025-11-14 12:01 | The last time you created/updated a URL so we can understand deployment app versions
Client Page Status | Final Presentation | Determines page status for the shared link
NOW Project
Hourly Project Rate | 325 | Standard hourly rate for most services | project_hourly_rate
Project Management Factor | 20% | Percentage markup for project management
Project Management Content | To support management and communication, a project manager and delivery lead will own all A8 tasks and clearly communicate needs. - Visibility to budget spend will be provided during the duration of the project - A8 will provide check-in agenda items and follow-ups - Abundance 360 to communicate to A8's shared inbox for easier collaboration and timely responses - Abundance 360 driven delay will result in additional PM time billed to manage timeline | Description text for the PM section. editable by you.
SA Expected Start Date | 2025-11-24 | Project start date
Total Project Months | 1 | Expected project duration | project_duration
NEXT Support Retainer
Post-Launch Hourly Rate | 220 | Post-launch rate, a zero here will hide the workstream/section | retainer_hourly_rate
Post-Launch Hours Per Month | 30 | Post-launch hours per month, a zero here will hide the workstream/section | retainer_hours_per_month_sold
Post-Launch # of Months | 0 | Post-launch months, a zero here will hide the workstream/section | retainer_months_sold
Post-Launch Support Content | Hours dedicated to post go-live support. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.) | Description text for the post-launch section
Additional Notes + Considerations
Additional Notes | - The assumptions content in this scope is based on information and discovery during the sales evaluation and is subject to change during the project if additional challenges or barriers are discovered. - A8 is a Time & Materials agency, we will provide transparent budget tracking throughout the project and change orders will require approvals. - We interchange between A8 and Aptitude 8 in this document. | Description text for below the investment summaries, but above the later phase workstreams

## Calculations
HubSpot Property
Calculated Project Details
Total Service Hours Hours | 31 | Total amount of Input rows
Total Project Management Hours | 6 | Based on PM % in Config Sheet
Total Project Hours Sold | 37 | Service + PM | project_hours_sold
Total Retainer Hours Sold | 0
Total Engagement Hours Sold | 37 | This should match exactly to the investment block on the HTML Page | sold_hours
Deal Amount | 12025 | This should match exactly to the investment block on the HTML Page | amount
Expected End Date | 2025-12-24
Expected Project Hours/Month | 31
Linear Expected Project Hours/Week | 8
Peak Project Expected Hours/Week | 9.6
Low Project Expected Hours/Week | 4
Dev Work Percentage | 0% |  | dev_work_pct
SE Work Percentage | 37.84% |  | se_work_pct
Calculated Function Summary
| Sum of Hours | Percent of
Consulting | 0 | 0%
Development | 0 | 0%
Project Management | 6 | 16.22%
Solutions Engineering | 14 | 37.84%
Strategy | 17 | 45.95%
Sum of Function-Based Hours | 37 | 100%
Calculated Ranges | Low Hours | High Hours
Project Service Estimates: | 22 | 37
Project Management: | 4 | 7
Post-Project Support: | 0 | 0
Hour Estimates: | 26 | 44
Investment Ranges: | 8450 | 14300
SOW Summarized Line Items
Workstream | Total Hours | Total Investment
Analysis | 4 | 1300
Discovery | 9 | 2925
Documentation | 4 | 1300
Mobilization | 3 | 975
Planning & Roadmap | 4 | 1300
Technical Analysis | 7 | 2275
Project Management | 6 | 1950
Post-Launch Support | 0 | 0