## Phase 1 Sales & Marketing Hub
c |  | MD Integrations
ID | Epic | Customer Story | Suggested Path | Estimated Low Hours | Estimated Hours | Estimated High Hours | Team | Priority | WHY | Implementation Team | Assumptions | Est. Hours | Phase | POC
|  |  | Total Estimated Project Hours: | 267.5 | 299.75 | 332
|  |  |  | 65537.5 | 73438.75 | 81340
ADMIN
1 | Full Instance Setup for Operational Readiness | As a HubSpot admin, I need to configure the foundational CRM, marketing, sales, and service tools in our new HubSpot instance so that all teams can begin using the system effectively and consistently from day one. | 🟢 Step 1: Configure Account Defaults (timezone, currency, branding) Step 2: Enable duplicate management Step 3: Connect email sending domain: @mdintegrations.com | 2 | 3.5 | 5 | Admin | High
4 | Record Form & Page Layout Customization | As a HubSpot admin, I need to customize the record forms and page layouts for contacts, companies, deals, and tickets so that users across marketing, sales, and service can view and input the most relevant information quickly, improving efficiency, consistency, and data accuracy across teams. | 🔴 Add examples - Waiting on HS purchase | 3 | 4 | 5 | Admin | High
5 | Data Migration from Copper CRM | As a HubSpot admin, I need to migrate data from Copper into HubSpot, so that all historical contact, company, and deal, data is preserved and accessible in the new system without manual entry. | 🟢 Step 1: Data Audit & Mapping ---Review exported data from Copper ---Map Copper fields to HubSpot standard/custom properties ---Identify any gaps, custom properties needed, or data cleanup required Step 2: Property Setup in HubSpot ---Create necessary custom properties in HubSpot (contacts, companies, deals) Step 3: Data Cleanup & Prep ---De-duplicate records ---Reformat fields (e.g., dates, picklists) ---Align IDs for relational imports (e.g., linking contacts to companies and deals) Step 4: Import Execution ---Import Companies > Contacts > Deals (in this order) ---Validate imports and check for errors ---Import deal associations to companies and contacts Step 5. QA & Post-Import Validation ---Spot-check 10–15 records from each object ---Ensure associations, owners, stages, and fields carried over accurately ---Review activity timeline, if included in migration | 13 | 14 | 15 | Admin | High
6 | HubSpot Training & Documentation | As an admin, I want comprehensive HubSpot training and access to clear documentation, so that I can confidently use the platform, adopt best practices, and reduce dependency on others for day-to-day tasks. | 🟢 Step 1: Preparation ---Roles mapping, team grouping, agenda building, permission setup Step 2: Sales Hub Training ---5 team-specific sessions (very minimal CRM experience) Step 3: Marketing Hub Training ---2 sessions (Maria has used HS in the past) Step 4: Asset Creation ---Custom decks, recordings, playbooks, SOPs Step 5: Q&A & Post-Training Follow-Up ---Answering questions, feedback, final documentation | 8 | 14 | 20 | Admin | High
|  |  | ADMIN TOTAL | 26 |  | 45 | Admin | High
|  |  |  | 35.5 |  |  | Admin | High
MARKETING | [6 empty] | Marketing | High
8 | Contact Us Form | As a marketer, I want to create a high-converting webform experience for prospective partners, so we can capture qualified leads, understand their integration needs, and seamlessly hand them off to our sales team for follow-up. | 🟢 Step 1: Create HubSpot Form ---replicate Current Form Step 2: Set up Notifications ---Assign & Notify Alyssa (a.fox@mdintegrations.com) - eventually round robin to BDRs | 2 | 2.5 | 3 | Marketing | High
9 | Active List Management | As a marketer, I need active lists set up based on key contact properties and behaviors, so I can easily send targeted and segmented communications to the right audience. | 🟢 Step 1: Define segmentation criteria --- See 'GTM data flows' tab Step 2: Create list filters and segmentation logic | 2 | 3.5 | 5 | Marketing | High
10 | Marketing Email Template Build | As a marketer, I need branded email templates built in HubSpot so I can easily create and send consistent, professional marketing emails without having to design each one from scratch. | 🔴 Step 1: Requirements gathering --- 2 templates - Do we have design? Step 2: Build template using HubSpot drag-and-drop editor | 2 | 3 | 4 | Marketing | High
11 | Subscription Type Setup | As a marketer, I need subscription types set up in HubSpot so that contacts can manage their email preferences and we can stay compliant with email regulations while sending targeted communications. | 🔴 Step 1: Requirements gathering ---Two types: Pricing & Marketing? Step 2: Create subscription types in HubSpot Step 3: Customize default unsubscribe page (copy, design, branding) | 1 | 2 | 3 | Marketing | High
12 | Lifecycle Stage Configuration | As a marketer, I need lifecycle stages set up and standardized in our CRM so we can accurately track where each contact is in the customer journey and trigger the right communications and handoffs between teams. | 🟢 The Business Process Map will help a lot with this one Step 1: Customize Lifecycle Stage Property ---Customize the default HubSpot lifecycle stage property with new values or mapping. 1. Lead- Generated by client through a formal interaction with our marketing system (form, call, referral) 2. MQL-Validated by marketing to be an ICP fit 3. SAL-Validated by marketing to be ready to engage in a sales discussion (urgency) 4. SQL-Validated by sales to be ready to purchase (urgency, budget) 5. Customer - Deal Moved to Close won Step 2: Audit Existing Data ---Review current contacts to identify if existing data should be retroactively updated to match the new model. Step 3: Create Lifecycle Workflows ---Build automation to move contacts between lifecycle stages based on defined behaviors (form fills, meeting booked, deal created, etc.). | 3 | 9 | 15 | Marketing | High
13 | Lead Nurturing Sequences | As a marketer, I want to set up lead nurturing email sequences based on the information provided in form submissions, so I can deliver personalized and segmented messaging to nurture leads more effectively | 🔴 Step 1: Collect email content ---Draft 3–5 emails per sequence tailored to segments. Need from Tallwave Step 2: Build Emails in HubSpot ---Create and format marketing emails using templates. Step 3: Set Up Workflows ---Create automated workflows for each nurture sequence. Step 4: Add Logic and Branching ---Include branching logic based on engagement (clicks, opens, form fills). Step 5: QA and Testing ---Test emails, links, workflow logic, and enrollment triggers. | 5 | 8 | 11 | Marketing | High
14 | Lead Scoring Implementation | As a marketer, I need a lead scoring model set up in HubSpot so that we can automatically qualify leads based on their engagement and fit, prioritize outreach for the sales team, and improve overall conversion rates. | 🟢 DISCOVERY ONLY IN PHASE 1 Step 1: Discovery & Criteria Definition ---Meet with stakeholders (marketing + sales) ---Define behavioral vs. demographic/firmographic scoring factors ---Align on thresholds for MQL, SQL, etc. BUILD IN A FUTURE PHASE Step 2: Build the Score Model in HubSpot ---Add scoring rules for each factor (e.g. page views, form fills, job title) ---Set up negative scoring criteria (e.g. unsubscribes, bounces) Step 3: Testing & QA ---Apply score to test records ---Ensure scoring is working and thresholds behave as expected Step 4: Iteration + Training/Documentation ---Create documentation for sales/marketing ---Review with team and iterate if needed | 0 | 2.5 | 5 | Marketing | High
15 | Marketing Reports & Dashboards | As a marketer, I need reports and dashboards built in HubSpot so I can track performance across channels, monitor lead conversion, and make data-driven decisions about where to focus our marketing efforts | 🟢 Step 1: Define Report Types & Data Sources ---See 'GTM Data Flows' Marketing Ops & Paid Media category (25) Step 2: Build Custom Reports ---Create and configure reports with filters, date ranges, and visuals. Step 3: Build Dashboards ---Group reports into usable dashboards Step 4: QA & Validate Data ---Test filters and metrics to ensure accuracy | 5 | 10 | 15 | Marketing | High
16 | Nurture Disqualified Leads Based on Disqualification Reason | As a marketer, based on the disqualified reason I need contacts to get enrolled in X campaign so that we can still nurture them | 🔴 Step1: Review & Finalize Disqualification Reasons ---Align with the sales team on the list of disqualification reasons. Step 2: Create Lists for Each Disqualification Reason ---Build active lists segmented by reason (e.g., “Not Ready,” “No Budget,” “Wrong Fit”). Step 3: Build Nurture Email Campaigns ---Draft email templates for each reason-specific nurture stream. ---Set up automated email workflows. Step 4: Workflow Configuration ---Create workflows that trigger based on disqualification reason and enroll contacts into appropriate campaign. Step 5: Test Automation ---Run test contacts through the workflows to ensure correct enrollment and email logic. | 3 | 6 | 9 | Marketing | High
17 | Blog Management in HubSpot | As a marketer, I want to manage and publish blog content directly from HubSpot, so that I can easily create, schedule, optimize, and track blog performance in one centralized platform. | 🔴 Step1: Set Up Blog Tool in HubSpot ---Configure blog settings: domain, blog name, URL structure, and language. Step2: Create Blog Template ---Build or customize a blog template for consistent branding and layout. Step3: Configure SEO Settings ---Set up meta descriptions, featured images, and optimize blog settings for SEO. Step4: Set Up Blog Subscription Options ---Enable blog subscription forms and email notifications for new posts. Step5: Schedule and Publish Test Post ---Publish a draft post to validate layout, design, and email alerts. Step6: Reporting Setup ---Create basic dashboards for blog traffic, CTA performance, and subscriber growth. | 3 | 6.5 | 10 | Marketing | High
High
|  |  | MARKETING TOTAL: | 26 |  | 80 | Marketing | High
|  |  |  | 53 |  |  | Marketing | High
SALES | [6 empty] | Sales | High
18 | Form Submission Alert | As a sales user, I want to be alerted when a contact fills out a form, so I can respond quickly and take the appropriate next step in the sales process. | 🟢 Step1: Automated email,task? Alert to Alyssa (a.fox@mdintegrations.com) - Right now, Leila, Alyssa and Marc all get the alert email - continue or just Alyssa? | 3 | 3 | 3 | Sales | High
19 | Automated Follow Up Email | As a sales user, I need an automated email to go out to the contact once they fill out the form so that I can make sure they know that I'll be reaching out and provide my HubSpot meetings like so that they can schedule on their own | 🟢 Step1: Trigger email once contact is assigned - Content in map - Need to add meetings link and Intake form? | 3 | 3 | 3 | Sales | High
20 | Follow-Up and Routing Automation | As a sales user, I want to automatically send two follow-up emails to a prospect who hasn't responded, and then route them to marketing, so I can stay focused on engaged leads while ensuring unresponsive prospects continue to be nurtured. | 🟢 1. Email 1 - X days post follow up - Content Needed 2. Email 2 - X days post follow up - Content Needed 3. Add to marketing list - List Name Should the 'Follow up' just be a sequence | 3 | 4 | 5 | Sales | High
21 | Deal Creation | As a sales user, I want the ability to create a deal once I've determined that a prospect is a good fit, so I can begin tracking them through the sales pipeline. | 🟢 Step1: Deal Form Step 2: Page Layout customization | 2 | 3.5 | 5 | Sales | High
22 | Sales Pipeline Configuration | As a sales user, I need a customized sales pipeline set up in HubSpot so that our team can effectively track and manage deals through each stage, ensuring a smooth and organized process for converting leads into customers. | 🟢 Step1: Pipeline Creation ---Create custom pipeline in HubSpot and define deal stages 1. Qualified 2. Intro Call 3. Follow up 4. Intake Form Received 5. Contract Sent 6. Negotiation 7. Contract Signed 8. Integrating 9. Integration Complete/Live? Or new stage for Live? Step 2: Stage Property Configuration ---Set required properties per stage (e.g. close date, deal amount) Step 3: Automation Setup ---Add workflows like stage entry alerts, task creation, or stage-based emails Step 4: Testing & QA ---Test pipeline creation, movement, and notifications | 3 | 3 | 3 | Sales | High
23 | Intro Call Playbook | As a sales user, I want a structured lead playbook to follow and complete during my first intro call, so I can ensure I'm gathering the right information consistently. | 🟢 Step 1: Playbook Build ---Set up the playbook Questions to ask Leads: First call/meeting needs to be focused on asking questions and information collection: 1. Can you please share an overview of your company? 2. Do you have a clinical network in place currently? If so, what types of clinicians are currently servicing your visits? How is that working out? 3. Are you legitscript certified? 4. What kinds of clinician specializations do you need? 5. What are your current consult volumes or estimated consult volumes? 6. What states are you currently servicing? 7. What platform do you currently have in place? 8. Are you a cash pay business or insurance, or both? 9. Are you primarily looking to have asynchronous or synchronous visits? 10. Will you be able to integrate with our API? Do you have a dev team to help with the API integration? Step 2: Testing & QA ---Test the playbook on a record to ensure it's logging data and functioning correctly | 3 | 4 | 5 | Sales | High
24 | Call No-Show Sequence | As a sales user, I want an automated sequence for contacts who miss scheduled calls, so I can efficiently follow up and re-engage them without manual effort. | 🟢 Step 1: Sequence Build in HubSpot Build sequence: emails, tasks, delays, branching logic 1. Email 1 - X days post intro call missed - Content Needed 2. Email 2 - X days post intro call missed - Content Needed 3. Add to marketing list - List Name Step 2: Testing & QA Test each sequence end-to-end on test contact | 3 | 4 | 5 | Sales | High
25 | Disqualification Reason Prompt | As a sales user, when I disqualify a contact, I want to be prompted to provide a reason, so we can track and analyze disqualification trends over time. | 🟢 Step 1: Conditional Logic Setup | 3 | 3 | 3 | Sales | High
26 | Streamlining the Pre-Contract Process with Quotes | As a sales user, I want to implement a structured quote process before we send a contract, so that we avoid wasting time on legal reviews for deals that haven't been budget-approved or formally accepted, and improve efficiency in our sales cycle. (min 40:44) | Proposed Solution: -Introduce a formal quote/proposal stage before contracts are sent. -Use HubSpot Quotes or Proposals in Sales Hub to deliver: Scope of work, Pricing details, Validity window (e.g. “Quote valid for 5 days”), Optional approval or sign-off mechanism -Only after quote acceptance does the deal advance to the Contract Sent stage. Acceptance Criteria: 1. Sales Process Update -New deal stage added: Proposal Sent or Quote Delivered -Contracts can only be sent from Proposal Accepted or Quote Approved stage 2. Proposal/Quote Functionality -Sales team uses HubSpot Quotes or custom proposal templates -Includes pricing, deliverables, and terms summary -Validity period is enforced (e.g., quote expires after 5 days) 3. Internal Workflow -Sending a proposal triggers internal tracking (e.g., task reminder to follow up) -Proposal viewed = sales alert -Acceptance of proposal = trigger to prepare contract 4. Reporting -Can track # of proposals sent vs contracts generated -See average time between proposal and contract stages -Identify drop-off before contracts go out | 13 | 13 | 13 | Sales | High | Current Challenge: 1. Contracts are being sent too early — often based on a verbal “yes” or general interest. 2. No formal checkpoint to confirm budget, scope alignment, or internal approvals. 3. Time is wasted by both sales and legal teams reviewing contracts that never go anywhere. 4. We're using a generic contract template as a stand-in for an actual proposal.
27 | OPTION 1: Pricing Properties for Contract Creation | As Chief of Staff, I want custom properties where sales can input pricing details, so I can easily find, view, and copy the necessary information when drafting contracts. | 1. Create properties (see Copper) 2. Create a tab in the deals view that Vicky can easily go to | 3 | 1.5 | 0 | Sales | High
28 | OPTION 2: Pricing Properties + DocuSign Integration | As a Chief of Staff, I want custom pricing properties populated by sales, integrated with DocuSign, so I can quickly generate accurate contracts without manual data entry. (screen share min 39:45) | DocUSign integration | 0 | 9 | 18 | Sales | High
29 | Contract Follow-Up Automation | As a Chief of Staff, I want the ability to enroll contacts into a contract follow-up sequence, so that if a contract hasn't been signed, automated reminders are sent to keep the process moving forward without manual follow-up. | 🟢 Step 1: Sequence Build in HubSpot ---Build sequence: emails, tasks, delays, branching logic 1. Recreate Vicky's task process from Copper and follow up emails she normally sends into a sequence 2. Based on what's chosen above, either contract sent stage or contract status property or once update via integration Step 2: Testing & QA ---Test each sequence end-to-end on test contact | 3 | 3 | 3 | Sales | High
30 | Deal Forecasting Accuracy | As a sales leader, I want to require an amount to be added to a deal by a specific stage in the pipeline, so we can accurately forecast revenue and ensure only qualified, realistic opportunities are influencing our projections. | 🟢 Step 1: Build logic --- When Estimated Consult Volume >5,000, then add as VIP --- Add VIP tag in the deal card view | 1 | 1.5 | 2 | Sales | High
31 | Email Integration with HubSpot | As a sales user, I want to integrate my email inbox with HubSpot, so that my emails are automatically logged on contact records and I can send and track emails directly from within the CRM without switching tools. | 🔴 Step 1:Confirm Email Platform ---Verify whether users are using Gmail or Outlook Step 2: Connect Inbox in HubSpot ---Each user connects their inbox via HubSpot > Settings > General > Email. Step 3: Enable Email Logging & Tracking Settings ---Set default preferences (log emails, track opens/clicks). Step 4: Configure Email Extension ---Install and configure Chrome Extension (Gmail) or Outlook Add-in. Step 5: Test Email Logging & Syncing ---Send test emails and confirm logging on contact records. Step 6: Train Users ---Quick demo or documentation on how to use email inside HubSpot (logging, tracking, templates). | 2 | 3 | 4 | Sales | High
32 | HubSpot Meetings Tool | As a sales user, I need to use the HubSpot Meetings tool so that prospects can easily book time on my calendar without back-and-forth emails, allowing me to streamline scheduling, reduce friction in the sales process, and stay organized with automatic contact and activity tracking. | 🟢 Step 1: Connect User Calendars ---Guide users to integrate their Google or Outlook calendars with HubSpot. Step 2: Create Meeting Links ---Set up individual and team meeting links with branding, availability, buffers, custom questions, and follow-up settings. Step 3: Routing Setup (Optional) ---If using round-robin or team meetings, configure routing logic and assignment rules. Step 4: Embed on Website or in Emails ---Add meeting links to CTAs, website forms, or email templates. Step 5: Testing & QA ---Test links for functionality, calendar sync, and contact creation. 1. Meetings tool set up and training - Send invite through zoom for a 30 minute slot *pay attention to time zones* - Brief agenda - include this in the invite: 1. Intro’s, 2. Prospective Client’s Company Overview, 3. MDI Overview, 4. Next steps | 3 | 3 | 3 | Sales | High
33 | Sales Email Templates & Snippets | As a sales user, I want prebuilt email templates and snippets so I can send consistent messaging faster | 🔴 Step 1: Import Existing Copy ---Need from Tallwave Step 2: Build Email Templates in HubSpot (5) ---Create and format templates, including personalization tokens and links Step 3: Build Snippets ---Create short text blocks (e.g., value props, product blurbs, responses to FAQs) Step 4:Internal Testing & Review ---Test personalization, formatting, links; get sales team feedback | 3 | 4 | 5 | Sales | High
34 | Sales Reports & Dashboards | As a sales manager, I need reports and dashboards built in HubSpot so I can monitor deal pipeline health, track rep performance, forecast revenue, and identify areas for improvement across the sales cycle. | 🟢 Step 1: Define Report Types & Data Sources ---See below Step 2: Build Custom Reports ---Create and configure reports with filters, date ranges, and visuals. 1. Deal Pipeline by Stage – Visual representation of where deals stand 2. Deal Forecast by Close Date – Expected revenue this month/quarter 3. Revenue by Rep – Closed won amounts per rep 4. Average Deal Size by Pipeline or Rep 5. Win Rate by Pipeline Stage 6. Deal Velocity (Time in Each Stage) 7. Activity Report: Calls, Emails, Meetings by Rep 8. Lead Source to Deal Conversion Rate 9. Lost Deals by Reason 10. Deals with No Activity in Last X Days Step 3: Build Dashboards ---Group reports into usable dashboards 1. Sales Overview Dashboard 2. Pipeline summary, forecast, win/loss ratio, activity overview 3. Sales Rep Performance Dashboard 4. Individual KPIs like closed revenue, outreach volume, win rate 5. Forecast Dashboard 6. Weighted pipeline, expected revenue by week/month/quarter 7. Deal Movement Dashboard 8. Stalled deals, aging deals, deals pushed frequently 9. Lead Conversion Dashboard 10. Source → SQL → Opportunity conversion tracking Step 4: QA & Validate Data ---Test filters and metrics to ensure accuracy | 8 | 11.5 | 15 | Sales | High
35 | Parent–Child Company Relationships | As a sales user, I want to set up parent-child relationships between companies in HubSpot so I can understand and report on account hierarchies and manage them more effectively for the aggrigator process. (min 39:23 onboarding) | 🟢 Step 1. Data Audit ---Review existing company data for accuracy, duplicates, naming conventions, and readiness for association Step 2. Property Configuration ---Ensure standard company properties (or custom ones if needed) are in place to reflect account hierarchy Step 3. Parent–Child Relationship Setup ---Use HubSpot’s native parent–child feature or import CSV with associations Step 4. Testing & Validation ---Spot-check relationships to ensure proper links, test filtering and reporting on account hierarchies | 3 | 3 | 3 | Sales | High
|  |  | SALES TOTAL: | 62 |  | 98 | Sales | High
|  |  |  | 80 |  |  | Sales | High
ON-BOARDING | [6 empty] | On-boarding | High
36 | Onboarding Trigger | As a sales user, I want to trigger an alert to the onboarding team by checking a "Ready for Onboarding" box, so they know when to begin their process without delay. | 🟢 Step 1: Create Custom Property ---Create a “Ready for Onboarding” checkbox property on deals or contacts Step 2: Build Workflow ---Create a HubSpot workflow that triggers when the checkbox is selected ---Auto create a deal in the On-boarding pipe Step 3: Configure Alerts ---Set up internal notifications, task creation, or ticket creation to notify onboarding ---alert Corey (corey@mdintegrations.com) Step 4: Test Workflow ---Run through tests to ensure the alert works and reaches the correct recipients | 3 | 4 | 5 | On-boarding | High
37 | Onboarding Pipeline Visibility | As an onboarding user, I want a dedicated pipeline to track the status of each onboarding project, so both I and the broader team have clear visibility into client progress. | 🟢 Step 1: Pipeline Configuration ---Create custom ticket pipeline in HubSpot with onboarding-specific stages 1. New 2. Kick off 3. Integrating 4. Live Step 2: Ticket Property Customization ---Create or update ticket properties to track critical onboarding data (e.g., Start Date, Key Milestones, Project Lead) Step 3: Automation Setup ---Create workflows to notify teams, assign owners, or trigger tasks based on pipeline stage movement Step 4: Visibility Setup ---Build filtered views or reports for onboarding managers and team members to monitor status Step 5: Testing & Validation ---Run through a test onboarding ticket to ensure flow works as intended | 3 | 4 | 5 | On-boarding | High
38 | Contracting Handoff Notification | As an onboarding user, I want to receive a notification from contracting (via Vicky) confirming that the client has completed their intake form or signed their contract, so I know when it’s appropriate to begin the rest of the onboarding process. | 🔴 Step 1: Build workflow ---Send internal notification to Corey (corey@mdintegrations.com) when a deal is moved to 'Contract Signed' stage Step 2: Test workflow with sample deals/contracts Move Onboarding pipe deal to Pricing/Ramp Up? | 1 | 1.5 | 2 | On-boarding | High
39 | Onboarding Introduction Email Template | As an onboarding user, I need a standardized email template for introducing myself to the client after the sales team has made the handoff, so I can ensure consistent communication and a smooth transition into the onboarding process | 🔴 Step 1: Create Template in HubSpot ---Design and structure the template - Need copy from Corey Step 2: Insert Personalization Tokens ---Add dynamic fields like contact name, company name, deal amount, etc. Step 3: Set Template Category and Folder ---Create On-boarding folder - add template in the On-boarding folder | 1 | 1.5 | 2 | On-boarding | High
2 | User & Permission Setup | As an admin, I need to set up HubSpot users, teams, roles, and permissions so that each team member has the appropriate access based on their responsibilities and can work efficiently within the system. | 🟢 Step 1: Review Org Chart & Define Teams ---Align on how users should be grouped by department, function, or brand. See User & Permissions sheet Step 2: Create Teams in HubSpot ---Set up HubSpot teams (with nested teams if applicable). Step 3: Define & Document Permission Sets ---Identify user types (Sales, Marketing, Service, Admin, etc.) and determine access levels. Step 4: Create Custom Roles & Assign Permissions ---Build out roles in HubSpot and apply permissions accordingly. Step 5: Invite Users & Assign to Teams/Roles ---Add users and apply correct teams and roles. Step 6: Test User Access & Make Adjustments ---Validate permission levels across record types and tools. Step 7: User Onboarding Guide or Training Session (Optional) ---Provide documentation or live walk-through of user experience. | 3 | 4.5 | 6 | Admin | High
3 | Custom Properties for Data Tracking | As an admin, I need custom properties created in HubSpot to track specific data points relevant to our business processes, so we can capture, report on, and use that data effectively across teams. | 🟢 Step 1: See first tab 'New Properties' (13) | 2 | 2.5 | 3 | Admin | High
|  | Buffer Times since some of this process is still being sorted out/identified |  | 0 | 5 | 10 | On-boarding | High
|  |  | ON-BOARDING TOTAL: | 13 |  | 33 | On-boarding | High
|  |  |  | 23 |  |  | On-boarding | High
Project Management | [7 empty] | High
99 | Project Kickoff, Onboarding, and Closeout | MDI needs a structured project management across kickoff, check-ins, and closeout so that our teams stay aligned, deliverables stay on track, and we have clear visibility into progress, decisions, and next steps throughout the engagement. | To support management and communication, a project manager and delivery lead will own all A8 tasks and clearly communicate needs to MDI. | 76 |  |  |  | High
98 | Recurring Project Check-ins |  | Consistent project status meetings to ensure alignment and address emerging needs. |  |  |  |  | High
97 | Project Administration |  | Administrative support to ensure efficient project execution. |  |  |  |  | High
|  |  |  | 76 |  |  |  | High

## Sheet2
MQL
Conditions that they're treating (consults for derm, weight loss,
Service needs (any) | cash and consult volume is high + urgency --> SAL
Service Type = Asynch
Est consult vol is > 2k
payment methods cash
Phase 2 = Referral
DQ (Lead Status = Unqualified)
if looking to prescribe testosterone or controlled substances | SQL can only occur after lawyer completes background check
Don't yet have any volume | HubSpot form to collect data
Service Type doesn't include asynch | What should happen if someone is denied? Lawyer might have language that Alyssa/Vicki sends
payment method not cash | Automation to lifecycle stage = DQ'ed