## Opt. Assessment
Workstream | Service_Title | Customer_Story | Suggested_Path | Assumptions
Mobilization | Project Setup | As a project team and client stakeholders, we want to align on project scope, timeline, deliverables, and stakeholders so that the project begins with shared clarity, expectations, and the right people involved. | 1) Internal alignment on scope, sales deliverables, and expectations. 2) External kickoff with client stakeholders to review project plan and approach. 3) Review of sales deliverables and recordings to inform interview agendas. 4) Stakeholder mapping to ensure comprehensive discovery coverage. | • Includes one internal alignment session and one external kickoff. Client to provide sales materials, SOW, and transcripts in advance. • Stakeholder mapping limited to one matrix; client responsible for providing full contact list. • Excludes role training or ongoing stakeholder onboarding.
Technical Assessment | HubSpot Portal Audit | As a technical consultant, I want to conduct a high-level HubSpot audit to determine current feature usage so that we understand existing portal capabilities and utilization. | Targeted audit of duplicates, associations, Golden Rules workflows, and integrations. | • Includes review of core objects (contacts, companies, deals) and up to five connected integrations. Excludes complete workflow documentation; issues flagged only. Requires client to grant Super Admin access.
Technical Assessment | Data Quality Assessment | As a data analyst, I want to assess current data quality and structure so that we can identify cleansing and migration requirements. | Deep dive into duplicates, association failures, and enrichment gaps (Clay, Zapier, partners). | • Includes review of up to 3,000 sample records. • Focus limited to duplicates, associations, and enrichment mismatches. • Excludes full data cleanse; recommendations only. • Client to provide CSV exports and data lake field mapping.
Discovery | Overview Interview | As a strategy consultant, I want to interview end users so that we understand daily workflows and pain points. | Conduct role-based interviews (focus on “day in the life”). | • Includes up to 1 session with project decision makers and POCs. • Excludes role-specific training. • Client to schedule participants.
Discovery | Marketing Operations Interviews | As a strategy consultant, I want to interview marketing ops team so that we understand campaign processes and lead management. | Explore campaign setup, tracking variables, and new property hierarchy (Engagement → Intent). | • Limited to 1–2 executives and 2–4 end users. • Focused on campaign processes, tracking, and handoffs. • Excludes technical build or media buying.
Discovery | Sales Operations Interviews | As a strategy consultant, I want to interview sales ops team so that we understand sales processes and pipeline management. | Explore SDR pipeline, duplicates in deals/contacts, and Golden Rules enforcement. | • Limited to 1–2 executives and 2–4 end users. • Focus restricted to HubSpot sales processes. • Excludes downstream ERP or finance workflows.
Discovery | Customer Success/Support Interviews | As a strategy consultant, I want to interview customer-facing teams so that we understand customer journey and support processes. | Understand post-sale data handoff, associations, and customer lifecycle reporting. | • Limited to 1–2 executives and 2–4 end users. • Focused on CS use of HubSpot. • Excludes detailed support tooling (e.g., Zendesk).
Discovery | IT/Technical Stakeholder Interviews | As a technical consultant, I want to interview IT stakeholders so that we understand technical constraints and capabilities. | Focus on data lake sync, integration ownership, and governance. | • Includes up to 2 interviews with IT stakeholders. • Requires client IT participation. • Excludes detailed ERP or finance system design.
Discovery | Executive Stakeholder Workshop | As a strategy consultant, I want to conduct interviews with executive stakeholders so that we understand business objectives and success criteria. | Validate findings, align on success criteria, and confirm future-state architecture vision. | • One workshop, up to 2 hours. • Workshop focused on confirming business goals and aligning requirements. • Excludes solution design; captured separately. • Client must provide 3+ executive stakeholders.
Requirement Design | User Story Development | As a strategy consultant, I want to create detailed user stories so that we have clear development requirements. | Break down epics (duplicates, governance, architecture, workflows) into actionable stories. | • Includes up to 20 user stories with acceptance criteria. • Excludes backlog grooming or sprint planning. • Client to review and approve stories.
Analysis | Technical Requirements Documentation | As a technical consultant, I want to document technical requirements so that we understand system specifications needed. | Consolidate discovery into technical specs (APIs, integrations, security). | • Includes API, integration, and security requirements. • Excludes implementation. • Client IT must validate specifications.
Analysis | Business Requirements Documentation | As a strategy consultant, I want to document business requirements so that we have clear functional specifications. | Capture needs across Sales Ops, SDR, Marketing, CS. | • Includes documentation of functional requirements. • Excludes training documentation. • Client leadership must validate.
Analysis | Gap Analysis | As a strategy consultant, I want to conduct gap analysis between current and future state so that we identify what needs to be built/changed. | Compare current workflows + data integrity vs. desired end state. | • Includes review of APIs, data flows, and permissions. • Excludes implementation of fixes. • Client confirms desired future state.
Process Design | Process Mapping – Current State | As a strategy consultant, I want to map current state processes so that we document existing workflows. | Map lead lifecycle, Golden Rules, and duplicates pain points. | • Includes up to 5 process flows. • Excludes new automation builds. • Client validates diagrams.
Process Design | Process Mapping – Future State | As a strategy consultant, I want to design future state processes so that we define optimized workflows. | Redesign process leveraging HubSpot features (assoc. labels, dedupe, new variables). | • Includes up to 5 redesigned process flows. • Excludes technical configuration. • Client to approve future-state design.
Technical Design | Technical Architecture Design | As a technical consultant, I want to design technical architecture so that we define system structure and integrations. | Map HubSpot ↔ Data Lake sync, app governance, and permissioning. | • Includes one environment diagram + supporting notes.• Excludes configuration/implementation.• Client confirms data lake governance.
Validation | Requirements Validation Workshop | As a strategy consultant, I want to facilitate requirements validation workshop so that we confirm understanding with stakeholders. | Review requirements, highlight improvements, validate priorities. | • One workshop, up to 2 hours. • Workshop focused on confirming findings. • Excludes design decisions. • Client ensures participation from key stakeholders.
Planning | Project Planning | As a project manager, I want to create detailed timeline and resource plan so that we provide realistic implementation roadmap with priorities. | Draft roadmap with milestones, dependencies, quick wins. | • Includes one project plan with timeline + dependencies. • Excludes program management post-discovery. • Client confirms resource allocation.
Presentation | Executive Presentation Preparation | As a strategy consultant, I want to prepare executive presentation so that we effectively communicate findings and recommendations. | Summarize insights, quick wins, long-term plan. | • Includes one executive-ready slide deck. • Excludes additional department-level versions. • Client to confirm final audience.
Presentation | Final Presentation Delivery | As a strategy consultant, I want to deliver final presentation so that we present findings and get approval for next phase. | Deliver recommendations + path to implementation. | • Includes one 90-min session with leadership. • Excludes additional follow-up trainings. • Client ensures executive attendance.
Handoff | Implementation Handoff | As a strategy consultant, I want to facilitate handoff to implementation team so that we ensure smooth transition. | Transition requirements, architecture, and process maps to delivery team. | • Includes one handoff session + materials. • Excludes ongoing PM post-handoff. • Client provides receiving implementation team.
Support | Post-Engagement Support | As a strategy consultant, I want to provide post-engagement support so that we ensure successful transition to implementation. | Ongoing advisory + Q&A for delivery team. | • Includes up to 2 weeks post-engagement support. • Excludes ongoing managed services. • Client to direct all requests via single POC.