## Requirements from Discovery
Call Reference | Service Title | Requirement | Dept | Workstream | Clarification? | Note
CS/Order Management | CS Ticket Routing | Customer inquiry form submission creates a ticket, but today these are manually routed to the correct region and self-assigned from there. We would automate the ticket assignment round robin within the region | CS |  | Do we need to factor in request type as well?
CS/Order Management EMEA Direct Sales | Deal/Quote Creation | Currently quote creation is entirely manual - RFQ form fields would create + populate Tacton deal & quote. This RFQ form could be used by sales team or customers. RFQ submission checks for existing deal (creates if doesn't exist) > triggers Tacton deal creation + quote draft + task to review and fill in additional info. See EMEA avoma 35:55 | CS |  | Can we go ahead and have RFQ form submissions pre-populate portions of the quote?
CS/Order Management | Automated Quote Margin Business Approval | Unit pricing is variable, and as long as the requested quoted rate falls within certain margins, no approval is required. If the pricing falls outside those margins, the quote cannot be finalized until it's approved. They currently have to request business approval in Tacton. We would automate this so that if pricing requires approval, the approval request is sent automatically and auto routed based on region (they're currently manually selecting approver based on region)
CS/Order Management | Tacton -> HubSpot Product Library | Currently, Tacton -> doesn't sync to line items/product library, it syncs to Product Details custom object. HS deal creation requires part number, but product library doesn't 1:1 match, leading to users entering random part numbers if what they're looking for doesn't exist. Ideally, all new parts are created in SAP/Tacton and sync to HS so that everything is up to date | CS/Sales |  | Could Product Details update Line Items?
CS/Order Management | Quote Complete -> trigger send to Sales or Customer | There is a property to indicate whether the quote should be sent directly to the customer or to Sales to send to the customer. Automate this send based on 1) Quote Complete checkbox and sales/customer send | CS
CS/Order Management | Coordination with Cadre OCR PO reader | They're currently manually matching PO received to existing deal/quote in Tacton by searching the part number + account (customer). There are often mismatches (PO will have one name e.g. subsidiary and Tacton will show parent company). Cadre is working to cut down manual order creation via PO OCR reader. A8 facilitate automated order creation via PO
CS/Order Management | HS <> SAP Integration | Creating new Companies in HS should create Company in SAP + generate SAP BP code that syncs back to HS (this is all currently manual). For additional fields that should sync, see avoma 42:16-52-20
CS/Order Management | Project Custom Object | The team currently appends multiple POs received to the same deal (as orders come in over the life of the customer's project), even when the deal is already Closed Won. Instead, we should create a Project object to live a level above deals, then every time a new PO is received, a deal for that order is created and associated to the customer's Project. This will clean up forecasting/reporting and pipeline |  |  |  | example ERD in Lucid
CS/Order Management | Parts Custom Object? |  |  |  | Could we configure parts in a HS custom object (each variable tied to $) to then generate the quote to eliminate Tacton? See Tacton Reverse Demo for details
Distribution Support | Automate Deal Ownership | Automate deal ownership based on region (EMEA, NASAC, APAC) - currently manually set (Distie Support using a labeled map)
Distribution Support | Line Items with pricing | Now that pricing structure has been standardized (eliminated quantity-based price breaks), we could add pricing to the parts in the product library, but there is so much variability due to modifications (cable length, connectors, different antenna types), it's not practical to add each variation as a product
Distribution Support | Process Checklist? | Manual steps to gather customer information (reaching out to distributor or sales to get branch information for parent/child relationship etc) - a checklist would help the team stay on top of where they are in the process and avoid forgetting steps or anything falling through the cracks. See avoma 22:30-23:20
Distribution Support | Automate Part Number Totals | Team currently sums the totals for each part manually.
Distribution Support | Automare Reminders for Pending Registrations | Registrations often come through missing critical information, and the Distribution Support team must reach out to the distributor or salesperson for the missing information. They keep track of Pending Registrations via dashboard report. Automating this followup would free up some time for the team + increase pipeline velocity
Distribution Support | Tacton Integration Expansion | The distribution business model includes multiple distributors bidding for the same end customer's project (and sometimes they're also quoting the end customer for the same work). Taoglas must currently duplicate the same deal (in HS and Tacton) to prevent distributor information from being overwritten on all quotes (it changes all to the most recently entered distributor), so we end up with 1 deal per distributor (in HS and Tacton) instead of 1 deal with multiple distributor's quotes associated. If this is a hard limitation of Tacton, we could create a Distributor Bid custom object to track these and map each deal that must be created in Tacton to the Distributor Bid object in HS > assoc those to the 1 HS deal and update the deal with the winner's bid
Distribution Support | Distributor Portal or Distributor Form | To cut down on manual entry and overreliance on email, create distributor portal for distie login - they can update their own information as needed, indicate which branch, check status of quotes/orders/fulfillment, track order history, track revenue generated over time etc. See avoma 39:03-40:30 portal would be a greater value add than the distributor form, and may increase adoption If not portal, we could ask distributors to submit their quotes/registrations via a Taoglas form so that info is standardized and feeds directly into deal/registration etc. We understand many disties use their own forms exclusively and we wouldn't get 100% adoption, but even if we could get 50% it would be a real improvement |  |  |  | this is on track to be included in the OCR reader solution
Distribution Support EMEA Direct Sales | Duplicate Contact/Company/Deal Detection | They're currently manually checking whether a deal/registration already exists in the system - need a way to flag duplicates. See Distribution avoma 40:18, EMEA avoma 30:07
Distribution Support | Sales team ticketing pipeline with SLA for CS/Order Mgmt/Distribution Support | Currently no way to track communication (and lag time) between sales and service teams. This is creating massive friction with service not receiving timely responses, sellers missing emails or never replying. No way to hold teams accountable at the moment. A ticket pipeline would solve for messages being "lost" and not having a way to track response times
Distribution Support | Automated reminders to sales team for open tickets (see previous story) | In addition to the ticket pipeline, automate reminders for response. It is a reality that the sales team are on the road and busy the majority of the time and yes, emails sometimes fall through the cracks. Automated reminders + tickets would keep things on track
Distribution Support | Investigate email logging setup + train team on correct process | There is currently either an issue in the settings for email tracking, or a lack of knowledge around the correct process to select the contact/company/deal to log email activity to. This is currently used inconsistently and causes massive clutter and confusion when conversations end up on the wrong records. See avoma 46:47 (this is also addressed in the EMEA Direct Sales call - Sam spends a large amount of time ensuring everything is logged correctly and cleaning up records)
EMEA Direct Sales Distribution Sales | Parent/Child Companies | Ensure proper usage and staff training around maintaining parent/child company relationships. With hundreds of branches in the system with global customers, this gets messy fast when assoc labels are used inconsistently. See avoma 12:29 Thorough explanation in Distribution Sales avoma 11:24
EMEA Direct Sales | Automated Deal Followup | Currently there is a 60 day reminder to sales to check in, which is about right, and in some cases a bit early. Future state, this would be an automated message when a Project is open 60 days with no new deal/PO, then maybe every 2-3 weeks (could vary based on expected PO cadence)? See avoma 24:25 Automated reminders for sellers to reach out if project/deal value is above X amount (instead of automated message), or this could be based on a Company score, if implemented See avoma 28:39
EMEA Direct Sales | Part Bundles (e.g. Flexible Antenna + Connector) on Quote as Upsell | There are certain products that, even if they customer didn't ask to be quoted on a particular part, it just makes sense to go ahead and include it in the quote and the customer can choose to include it in their PO or not (think of it as passive upselling). See avoma 46:00
EMEA Direct Sales | Unified Sales Pipeline | Mentioned in the Strategy stories and confirmed by multiple stakeholders. Consolidate to one pipeline with channel specific properties/workflows as needed for direct vs distie etc differences. Sam discusses this in avoma 53:02 pipeline verified in sales workshop HERE |  |  |  | Verified stages meet PSCI team needs 23:52
EMEA Direct Sales | Record layouts and views | This is at least partly covered in the Speed to Lead scope, but could need further customization for pipeline specific needs or sales activity. See avoma 54:27
Marketing Discovery | Marketing Health Dashboards | Monitor unsubscribes/bounces > set to non-marketing; update contact info based on Zoominfo (e.g. when contacts change companies and Zoominfo has the updated company and email)
Marketing Discovery | CTA Promo Strategy | They use popups to promote upcoming webinars, new product videos, blog posts etc and would like recommendations re: when and how to display for best conversion. See avoma 15:32
Marketing Discovery | GA4 Integration
Marketing Discovery | Sales sequences | For nurture use and sales team automation (automated emails during qualification stage, reminders during followup, etc)
Marketing Discovery | Sales Team Connected Inboxes + Calendars with Meeting Links | This could also be Inside Sales instead of reps
Marketing Discovery | Web Order Nurture Drip | Taoglas would like to start sending nurture drips to customers who place web orders See avoma 43:05
Marketing Discovery | NPS Surveys | Taoglas would like to start sending out NPS surveys to customers See avoma 43:45
NASAC Direct Sales | Lead/Account Prioritization Based on Customer Tech Spend | Of a company's annual budget expenditure, what's being spent on tech product set (that would be winnable by Taoglas). Another way they're tracking tnis is at the Company object level in HS (i.e. aggregate Project value). See avoma 20:54 |  |  | Covered in Speed to Lead?
NASAC Direct Sales | Fyxer AI Integration: Notes from Sales Calls onto Deal Records | See avoma 22:46 |  |  | Covered by Cadre engagement?
NASAC Direct Sales | "Go Get PO" Custom Properties, Dashboard, Automation | Create properties, automation and reports to support monitoring expected POs (e.g. customer purchased 40k units and we know their run rate is roughly 40k every 6 months = predict when PO is due, ability to check-in proactively without digging). See avoma 46:24
PSCI | Forecast by Reseller | Project object should accommodate multiple company assoc (distie, reseller, end customer, up bidder, etc) and reports should be able to filter by these as well. See avoma 15:11 (further explanation at 17:37-19:25)
PSCI | New Part Number Creation | When teams were manually creating parts, they could get new parts added in 1-2 days. They later "automated" the process and it's now taking ~2 weeks because it's not working properly. The 2 week timeline causes them to lose business because resellers can't wait that long to get the part number and pricing to be able to quote end customers. Need to streamline/simplify new part creation in Tacton or possibly move part creation + quoting into HubSpot. See avoma 25:22-28:20, 48:12-50:22
PSCI | Reporting by Part Number for Inventory Management | If we know we're averaging 1,000 of xyz part per quarter (or EAU estimate), we need to make sure our inventory is stocked appropriately based on sales volume
PSCI | Sync Inventory (or be able to show In Stock) from SAP to HS | Sales team has no access to SAP (where inventory mgmt lives), must rely on CS for inventory/stock availability questions. We would love to see the part, pricing, inventory, stock availability, and lead time on the line item for that specificc part (one stop shop) instead of checking multiple platforms and relying on other teams to get this information. See avoma 32:35
Aerospace & Defense | Teams & Permissions | ITAR requirements for US citizens only - need ability to set teams and permissions to include/exclude other users from viewing deals and deal info as needed. See avoma 1:43-4:09, 8:01-9:14, 10:27-16:30, 31:47-33:00
Aerospace & Defense | A&D Web Inquiries Routing | Include industry on web forms so that A&D inquiries route directly to Kevin Blakeley or A&D team only (currently anyone can view)
Aerospace & Defense | A&D Lead Routing | Currently manual and dependent on someone recognizing a company as a defense company (e.g. Lockheed Martin). Ideally we'd be able to match on company to route directly to Kevin & Jeremy without it bouncing around through sales & CS first. See avoma 37:09-38:39
Finance and RevOps | Update Deal from Quote Data | Once quote is created, product/volume/timeline etc become much more accurate than early pipeline forecasting. The HS <> Tacton integration should update the HS deal when the quote is created. See avoma 30:58-31:46
Finance and RevOps | Lead Time and Forecasting at Individual Part Level (not Quote/PO) | Example: A customer is looking at 5 parts - one will be a fast turnaround and we expect a sooner production date + receive POs for this part more quickly, but these other parts are going to be longer term and we don't expect to see POs for these until the next year. See avoma 44:27-49:22
A8 + Cadre CS Discovery | BP Codes and Payment Terms Sync from SAP to HS | There is currently no integration between HubSpot and SAP. At minimum, BP Codes and Payment Terms that are changed in SAP should update in HubSpot
A8 + Cadre CS Discovery | Institutional Knowledge Discovery | We know the team relies heavily on institutional knowledge that's not documented anywhere, but no one is sure what all of those bits of knowledge are. We need to conduct discovery sessions with CS/Order Mgmt teams to uncover this information. For example: distributor shipping days (if they miss a Wednesday deadline, it won't ship til the following Wednesday), which manufacturing plants orders will ship from (e.g. customer requests production in Vietnam, but they aren't currently shipping from Vietnam, so production must take place in Taiwan),

## Cadre Initiatives
Speed to Lead RB2B, Clay
Chatbot for CS inquiries
Soft quoting tool
Email summary
Meeting notes to HubSpot
OCR Reading POs + enter into SAP
Shipping Confirmations + Tracking Information to Customers
CS Inbox management (Fin.AI)
Rapid Flare for more complex CS inquiries