## Input
Display | Workstream | Service_Title | Customer_Story | Suggested_Path | Assumptions | Estimated_Low_Hours | Estimated_High_Hours | Contracted_Hours | Requires_Clarification | Function | Library_ID | Project_ID | Internal_Notes | Task_Link
Now | Speed-to-Lead Architecture & Routing | Lead Scoring Architecture Audit, Optimization & Alignment to Speed-to-Lead | As a Marketing Operations leader, I need a validated and optimized lead scoring model that accurately reflects buyer intent and fit, so high-value opportunities are routed at the right time while unqualified contacts remain in nurture. | • Audit existing scoring architecture and workflows built by NXT • Validate current Taoglas scoring model (see Demand to Deal doc) • Align scoring thresholds to Speed-to-Lead framework • Rebuild or optimize scoring weights, values, and decay rules as needed • Configure scoring triggers tied to Clay/RB2B enrichment • Ensure model supports Tier classification | • RB2B & Clay are configured by Cadre • NXT to provide workflow documentation and technical walkthrough (recorded for reference) • Content creation is out of scope • Scoring model focuses on Speed-to-Lead needs | 18 | 22 | 20 | FALSE | Consulting
Now | Speed-to-Lead Architecture & Routing | Speed-to-Lead Qualification, Routing Logic & Tier Assignment | As a revops team, we need a unified Speed-to-Lead process in HubSpot that qualifies leads consistently, captures the information Inside Sales needs to determine Tier and vertical, and routes opportunities automatically to the right Sales owners, so that no high-intent lead is missed, Tier 3 and Unknown opportunities remain with Inside Sales, and Tier 1 and Tier 2 opportunities are quickly assigned to the correct Sales team. | • Build workflows to route scored leads to Inside Sales once they reach threshold criteria • Implement Speed to Lead routing logic • Build Inside Sales qualification process • Build automated routing from Inside Sales to the correct Sales owners (OEM, A&D, PSCI) for accept/reject • Build Sales accept/reject workflow with required rejection reason • Build automated routing for accepted leads based on Tier and regional routing rules • Build nurture-return workflow • Implement automated handoff notifications | • Final routing rules provided and approved by Taoglas • Downstream sales pipeline is out of scope for this engagement • Tools outside HubSpot are out of scope for setup or configuration | 40 | 55 | 48 | FALSE | Consulting
Now | Speed-to-Lead Architecture & Routing | Record Customization & Custom Views for Speed-to-Lead | As an Inside Sales and Sales team, we need HubSpot record layouts and custom views designed around the Speed-to-Lead process so that qualification fields are easy to find, scored leads are easy to work, and Tiered opportunities can be managed efficiently without missing any high-intent leads. | • Customize Contact, Company, and Deal record layouts to surface the qualification fields, Tier indicators, vertical, project value, and Speed-to-Lead routing fields • Build custom views and queues for Inside Sales (scored leads, Tier 3/Unknown leads, newly assigned leads) • Build custom views/queues for Sales teams (Tier 1/2 assignments by region and vertical) • Create views for Accept/Reject, nurture returns, and leads requiring follow-up • Ensure all views support segmentation, territory logic, and Speed-to-Lead workflow triggers | • A8 configures layouts and views only in HubSpot • Taoglas provides final approval of required fields and layout preferences • Record customization limited to Contact, Company and Deal objects only • Views are created for Inside Sales, Sales, and Marketing Ops | 2 | 4 | 3 | FALSE | Consulting
Now | HubSpot Data Hygiene and Remediation | Legacy Workflow & List Remediation for Speed-to-Lead Readiness | As a Marketing Operations team, we need to safely remediate legacy workflows, lists, and automation structures left over from the previous scoring system so the new Speed-to-Lead and nurture architecture can operate cleanly, without unintended triggers, broken dependencies, or conflicting logic. This ensures we avoid duplicate nurture enrollment, misrouted leads, and automation failures when the new scoring and routing go live. | • Export and triage all lists; identify those used as workflow triggers, suppression lists, nurture segments, and routing inputs • Audit legacy workflows to identify list-based triggers, re-enrollment risks, and unused scoring dependencies • Disable or archive legacy scoring workflows; remediate only active workflows that must remain operational • Rebuild or update essential lists required for nurture, qualification, or routing (minimal edits only) • Validate and adjust nurture workflow entry and suppression logic to prevent duplicate or unintended enrollment | • Taoglas will approve list archive recommendations • Scoring logic changes are handled entirely in the Lead Scoring story • Nurture content is provided by Taoglas • Routing logic changes are handled in the Speed-to-Lead story • Full list re-architecture is out of scope • Full workflow rebuilds are out of scope unless specified in the Speed-to-Lead or Nurture Architecture stories • Downstream sales process changes are out of scope | 15 | 30 | 23 | FALSE | Consulting
Now | HubSpot Data Hygiene and Remediation | Extended Workflow, List & Property Cleanup (Post-Triage Hygiene) | As a Marketing Operations team, we need to complete extended cleanup of unused workflows, legacy lists, outdated properties, and leftover automation dependencies that fall outside of the minimal remediation required for Speed-to-Lead readiness. This work reduces technical debt, prevents future logic conflicts, and improves long-term system performance and maintainability across HubSpot. | • Audit and archive unused, outdated, or redundant workflows not required for Speed-to-Lead. • Audit and archive obsolete lists; consolidate or update lists with outdated or conflicting logic. • Audit custom properties for duplication, legacy scoring leftovers, or unused fields; archive or standardize as appropriate. • Update or remove broken automation dependencies (legacy triggers, unused list references, obsolete property logic). • Document cleanup actions and provide recommendations for ongoing governance. | • Speed-to-Lead–critical lists, workflows, routing logic, and scoring changes remain in their respective stories • No new nurture strategy, segmentation logic, or scoring models will be created as part of this story • All archives/removals require Taoglas approval prior to execution • Large workflow rebuilds or new automation design are not in scope for this story • This cleanup is not required for Speed-to-Lead go-live; it is optional hygiene work to reduce technical debt | 15 | 25 | 20 | FALSE | Consulting
Now | Nurture & Segmentation Architecture | Audience Segmentation Framework & Subscription Governance | As a Marketing team, we need accurate segmentation and subscription structures so the right contacts receive the right campaigns and GDPR compliance is maintained across regions. | • Audit and refine segmentation (OEM, A&D, PSCI, GNSS) • Align subscription types to segmentation • Define opt-in vs. legitimate-interest rules by region • Standardize lead source taxonomy for Clay, RB2B, Web, Downloads | • Legal-approved GDPR rules provided by Taoglas • Sales sequences governed separately from marketing emails | 8 | 12 | 10 | FALSE | Consulting
Now | Nurture & Segmentation Architecture | Email Deliverability Audit & Warm-Up Strategy | As a Marketing Operations owner, I need correct domain configuration and warm-up planning to safely scale nurture and outbound campaigns without risking deliverability. | • Audit SPF, DKIM, DMARC, bounce rules, and domain alignment • Review sending patterns and subscription use • Create warm-up plan for nurture and outbound • Establish deliverability monitoring thresholds • Remediate any configuration issues | • Taoglas IT executes DNS changes • A8 only audits HubSpot email infrastructure | 5 | 10 | 8 | FALSE | Consulting
Now | Nurture & Segmentation Architecture | Nurture Workflow Architecture & Multi-Vertical Enablement | As a Marketing team, we need scalable nurture workflows that guide contacts through awareness, evaluation, and readiness stages, tailored to each vertical. | • Audit existing nurture workflows built by NXT • Build scalable nurture model for OEM, A&D, PSCI, GNSS • Identify vertical-specific content gaps • Build nurture workflows with behavior- and score-based enrollment | • Taoglas provides all content | 10 | 15 | 13 | FALSE | Consulting
Now | Clay → HubSpot Integration | Clay → HubSpot Mapping, Property Governance & Data Readiness | As a Marketing Operations owner, I need Clay’s enriched data flowing into HubSpot with correct property mapping so it is usable for scoring, routing, and segmentation. | • Define HubSpot properties required for Clay → HubSpot ingestion • Create naming conventions and governance • Provide mapping rules to Cadre • Configure workflows triggered by Clay-enriched contacts • Validate data supports scoring, segmentation, and routing | • Cadre owns Clay configuration • A8 governs HubSpot-side data structures and workflows | 8 | 12 | 10 | FALSE | Solutions Engineering
Now | Clay → HubSpot Integration | Clay → HubSpot Integration Configuration, Activation & Data Flow Enablement | As a Marketing Operations team, we need Clay’s enriched and scored contacts flowing into HubSpot reliably, mapped to the correct fields, and triggering scoring and routing workflows, so that high-intent and enriched leads can enter the Speed-to-Lead process without manual intervention. | • Configure the incoming Clay → HubSpot integration connection, including authentication, API setup, and connection validation • Coordinate with Cadre to finalize the Clay → HubSpot data structure, payload format, and field mapping • Validate that Clay-delivered data correctly populates HubSpot properties according to the agreed schema. • Conduct integration testing with Cadre, including sample payload tests and validation of edge cases (e.g., updates, new contacts, missing data). | • Cadre is responsible for all Clay-side configuration, scoring models, data enrichment, and outbound payload structure • A8 is responsible for ensuring HubSpot can correctly receive, store, and operationalize Clay’s data, but does not build or maintain Clay • Any Clay-side changes requested by Taoglas must be implemented by Cadre • Integration will rely on HubSpot’s native API limits and available features; middleware or custom integrations are out of scope • Testing includes validation of sample payloads provided by Cadre but does not include ongoing monitoring of Clay’s data quality | 12 | 20 | 16 | FALSE | Consulting
Now | HubSpot Reporting | Reporting & Analytics Architecture | As a leadership team, we need dashboards that clearly show funnel performance, conversion rates, lead quality, and revenue contribution across tiers and verticals. | • Build operational dashboards (volume, scoring, routing, acceptance) • Build sales conversion dashboards (Tier 1/2 → Deal) • Build nurture engagement dashboards • Build executive forecasting (traffic → leads → pipeline) | • Reporting relies on HubSpot data only • No external BI tools are included in scope | 10 | 15 | 13 | FALSE | Consulting
Now | Training & Documentation | Data Dictionary, Architecture Maps & Process Documentation | As an organization, we need clear, centralized documentation that explains our data structures, scoring logic, routing rules, workflows, segmentation, and GDPR/subscription governance so Marketing, Inside Sales, Sales, and Cadre understand and are aligned on the infrastructure and can operate the Speed-to-Lead model consistently. | • Create a Data Dictionary of all A8-created properties, workflows, reports & forms • Create Speed to Lead Architecture and Process Map • Document routing logic • Document segmentation and subscription governance | • A8 will document data structures and workflows as built or optimized within this engagement; documentation of unrelated/legacy objects is out of scope. • NXT will provide workflow documentation inputs, which A8 will validate and correct as needed • Taoglas is responsible for final approval of segmentation, GDPR rules, and subscription governance • A8 will deliver documentation in a digital editable format (likely to include google docs, lucidcharts and tango docs) • Any additional documentation for external systems (Clay, RB2B, IT-owned systems) must be provided by Cadre or Taoglas and is not authored by A8 | 20 | 30 | 25 | FALSE | Consulting
Now | Training & Documentation | Inside Sales Training on Qualification Process, Tiering & Routing | As an Inside Sales team, we need hands-on training in HubSpot so we know exactly how to work scored leads, update qualification fields, determine Tier, and understand how our actions trigger automated routing—so we can follow the Speed-to-Lead process correctly and avoid misrouting or lead leakage. | • Deliver a live HubSpot training session for Inside Sales focused on the qualification and routing tools built in this engagement • Train users on where scored leads appear in HubSpot and how to work them using the qualification properties (vertical, project value, discovery details, Tier determination) • Demonstrate how qualification inputs feed the automated routing logic (i.e., what happens when fields are updated) • Show Inside Sales how to identify leads that remain owned by them (Tier 3 and Unknown) and how to create and work deals in HubSpot | • Training covers HubSpot usage only—A8 does not provide sales methodology, discovery coaching, objection handling, or training on any external tools • A8 provides one virtual session (recorded); additional sessions must be scoped separately • Taoglas is responsible for ensuring attendance and internal adoption of the training content • Training covers the tools and workflows created in this engagement • HubSpot onboarding, CRM basics, or non–Speed-to-Lead training topics must be scoped separately | 4 | 6 | 5 | FALSE | Consulting
Now | Flex Hours | Flex Hours | Taoglas needs additional consulting capacity to take advantage of quick win opportunities in their current HubSpot instance. | • Hours may be used to supplement any of the above customer stories. | • Hours must be used for this scope of work and do not roll over to any subsequent projects | 12 | 12 | 12 | FALSE | Consulting
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Config
Configuration | Value | Description | HubSpot Property
GDrive + Deal Inputs
Company Name | Taoglas | Client company name for proposals
Google Folder |  | Needs to be manually input for the time being, will be set by the Pipedream automation
Deal Record ID | 49070494503 | HubSpot deal record ID, needs to be manually input for the time being, will be set by the Pipedream automation
Last Sync to HubSpot |  | The last time the story doc was sync'd to the HubSpot deal record
Solutions Architect |  | SA assigned to this project
Scoping Status | SA Building |  | scoping_status
Project ID | ------ | TBD on usage to facilitate project creation
Client HTML Page
Client Page URL | https://script.google.com/macros/s/AKfycbzGfZXXrB8GB7kt-FSeTA8sL0Rw3BzaXwifNA9CDpjsqe8NBn4EL159NLqLBYwGjqUw/exec?sheetId=1Rv87qq0mva5T4EEFp-Cnvy8NeE5SDgMmX41OR8i6z2I | The URL of the page that will be shared in Trumpet | customer_stories_client_url
Last Client Page URL Generated | 2025-11-18 10:12 | The last time you created/updated a URL so we can understand deployment app versions
Client Page Status | Final Presentation | Determines page status for the shared link
NOW Project
Hourly Project Rate | 245 | Standard hourly rate for most services | project_hourly_rate
Project Management Factor | 25% | Percentage markup for project management
Project Management Content | To support management and communication, a project manager and delivery lead will own all A8 tasks and clearly communicate needs. - Visibility to budget spend will be provided during the duration of the project - A8 will provide check-in agenda items and follow-ups - [Company] to communicate to A8's shared inbox for easier collaboration and timely responses - [Company] driven delay will result in additional PM time billed to manage timeline | Description text for the PM section. editable by you.
SA Expected Start Date | 2025-12-12 | Project start date
Total Project Months | 3 | Expected project duration | project_duration
NEXT Support Retainer
Post-Launch Hourly Rate | 0 | Post-launch rate, a zero here will hide the workstream/section | retainer_hourly_rate
Post-Launch Hours Per Month | 0 | Post-launch hours per month, a zero here will hide the workstream/section | retainer_hours_per_month_sold
Post-Launch # of Months | 0 | Post-launch months, a zero here will hide the workstream/section | retainer_months_sold
Post-Launch Support Content | Hours dedicated to post go-live support. These hours can be used for anything HubSpot related (reporting, training, iterations, additional asks, etc.) | Description text for the post-launch section
Additional Notes + Considerations
Additional Notes | - The assumptions content in this scope is based on information and discovery during the sales evaluation and is subject to change during the project if additional challenges or barriers are discovered. - A8 is a Time & Materials agency, we will provide transparent budget tracking throughout the project and change orders will require approvals. - We interchange between A8 and Aptitude 8 in this document. | Description text for below the investment summaries, but above the later phase workstreams

## Calculations
HubSpot Property
Calculated Project Details
Total Service Hours Hours | 226 | Total amount of Input rows
Total Project Management Hours | 57 | Based on PM % in Config Sheet
Total Project Hours Sold | 283 | Service + PM | project_hours_sold
Total Retainer Hours Sold | 0
Total Engagement Hours Sold | 283 | This should match exactly to the investment block on the HTML Page | sold_hours
Deal Amount | 69335 | This should match exactly to the investment block on the HTML Page | amount
Expected End Date | 2026-03-12
Expected Project Hours/Month | 76
Linear Expected Project Hours/Week | 18
Peak Project Expected Hours/Week | 21.6
Low Project Expected Hours/Week | 9
Dev Work Percentage | 0% |  | dev_work_pct
SE Work Percentage | 3.534% |  | se_work_pct
Calculated Function Summary
| Sum of Hours | Percent of
Consulting | 216 | 76.33%
Development | 0 | 0%
Project Management | 57 | 20.14%
Solutions Engineering | 10 | 3.534%
Strategy | 0 | 0%
Sum of Function-Based Hours | 283 | 100%
Calculated Ranges | Low Hours | High Hours
Project Service Estimates: | 179 | 268
Project Management: | 45 | 67
Post-Project Support: | 0 | 0
Hour Estimates: | 224 | 335
Investment Ranges: | 54880 | 82075
SOW Summarized Line Items
Workstream | Total Hours | Total Investment
Clay → HubSpot Integration | 26 | 6370
Flex Hours | 12 | 2940
HubSpot Data Hygiene and Remediation | 43 | 10535
HubSpot Reporting | 13 | 3185
Nurture & Segmentation Architecture | 31 | 7595
Speed-to-Lead Architecture & Routing | 71 | 17395
Training & Documentation | 30 | 7350
Project Management | 57 | 13965
Post-Launch Support | 0 | 0