## Defintions
Services RACI MATRIX
The person or team responsible for completing the task. There can be more than one responsible person for a task.
The person responsible for the overall outcome of the task. There should be one accountable person per task.
The person or group who provides input and advice on the task. There can be more than one consulted person for a task.
The person or group who needs to be kept up to date on the project's progress.
Purpose | This RACI chart provides a clear framework for defining roles and responsibilities across all stakeholders—both internally and with our clients. Its primary goal is to prevent confusion, eliminate overlap, and ensure that each individual knows their specific role in the project. By doing so, it promotes accountability, streamlines communication, and reduces the risk of missed responsibilities.
Value | For Aptitude 8, this RACI aligns team members on roles, reduces ambiguity, and enhances operational efficiency in our client engagements. For our clients, it establishes clear accountability and decision-making processes, fostering trust and streamlining approvals.
How it is Used | The RACI chart is a living document referenced throughout the project lifecycle to clarify expectations, guide role alignment, and resolve questions of ownership. For each row of the RACI, use the dropdown menu in each cell to designate who is Responsible, Accountable, Consulted, or informed. This does not always have to be one role if it makes sense for two roles to have the same level of involvement for the action described.

## RACI Matrix - Client (External (hidden)
Services RACI MATRIX
|  | Executive Sponsor | Sales Team Lead | Marketing Team Lead | Services Team Lead | Technical Lead | Project Management | Accounts Payable | Marketing Team Lead | Services Team Lead | Finance Lead | Technical Lead | Executive Sponsor | Sales Team Lead | Marketing Team Lead | Services Team Lead | Technical Lead | Project Management | Accounts Payable | Account Manager | Services Team Lead
PRIORITY | PROJECT DELIVERABLE / ACTIVITY | Client | [10 empty] | Aptitude 8
Project Management
Low | Meeting scheduling | [16 empty] | R
Medium | Project Management tool updates (will need to figure out how to break this up between A8 owned and Client systems | [12 empty] | A |  |  |  |  | A
High | Action item creation + accountability | [11 empty] | C |  |  |  |  | C
| Account readiness | [12 empty] | A |  |  |  |  | A
Scope adherence
Budget adherence
RAID log maintenance
Account Management
| Change order management | [11 empty] | C |  |  |  |  | C |  | R
| Billing inquiries & updates | [11 empty] | C |  |  |  |  | C
| Expansions | [11 empty] | C | I |  |  |  | C | I
| Escalations | [11 empty] | C | I |  |  |  | C | I
Check ins
Controls & Approvals
| Requirements sign-off | [11 empty] | A |  |  |  |  | A
| TRD/BRD sign-off | [11 empty] | C | I |  |  |  | C | I
Design sign-off
Change order sign-off
UAT completion sign-off
Training sign-off
Deployment sign-off
Project closure
Workstream owners (Epics)
| Training | [11 empty] | C | I |  |  |  | C | I
Data architecture
Integrations
Migrations
Sales
Marketing
Service
Operations
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Draft - Admin Activity Focus (hidden)
Services RACI MATRIX
|  | Executive Sponsor | Sales Team Lead | Marketing Team Lead | Services Team Lead | Technical Lead | Project Management | Accounts Payable | Project Manager | Finance Lead | Executive Sponsor | Principal Consultant | Project Manager | Technical Consultants | Solutions Engineer | Solutions Consultant | Full-Stack Developers | Account Manager | Finance Lead
PRIORITY | ACTIVITY | Client | [8 empty] | Aptitude 8
Project Management
| Account readiness | [9 empty] | C | A | C | I | I | I | I | R | I
| Meeting scheduling | [9 empty] | C | A | R | C | C | C | C | C | I
| Task management | [9 empty] | I | A | R | R | R | R | C | I | I
| Action item follow-up | [9 empty] | I | A | R | C | C | C | C | I | I
| Scope adherence | [9 empty] | C | R | A | C | C | C | C | I | I
| Budget adherence | [9 empty] | C | R | A | C | C | C | C | I | I
| RAID log maintenance | [9 empty] | C | A | R | I | I | I | I | I | I
Account Management
| Change order management | [9 empty] | C | A | C | I | I | C | I | R | I
| Billing inquiries & updates | [9 empty] | I | C | C | I | I | I | I | A | R
| Expansions | [9 empty] | C | A | C | I | I | C | I | R | I
| Escalations | [9 empty] | R | C | C | C | C | C | C | A | I
| Check ins | [9 empty] | C | C | A | I | I | I | I | R | I
Controls & Approvals
| Requirements sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| TRD/BRD sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Design sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Change order sign-off | [9 empty] | I | A | C | I | I | I | I | R | I
| UAT completion sign-off | [9 empty] | I | C | A | C | C | R | I | I | I
| Training sign-off | [9 empty] | I | C | A | C | C | R | I | I | I
| Deployment sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Project closure | [9 empty] | C | R | A | I | I | I | I | R | I
Workstream owners (Epics)
| Data architecture | [9 empty] | I | A | C | R | R | C | I | I | I
| Integrations | [9 empty] | I | R | C | A | R | C | C | I | I
| Migrations | [9 empty] | I | R | C | A | R | C | C | I | I
| Sales | [9 empty] | I | A | C | R | C | R | C | I | I
| Marketing | [9 empty] | I | A | C | R | C | R | C | I | I
| Service | [9 empty] | I | A | C | R | C | R | C | I | I
| Operations | [9 empty] | I | A | C | R | C | R | C | I | I
| Training | [9 empty] | I | A | C | C | C | R | C | I | I
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## RACI Matrix
Services RACI MATRIX
|  | Executive Sponsor | Sales Team Lead | Marketing Team Lead | Services Team Lead | Technical Lead | Project Management | Accounts Payable | Project Manager | Finance Lead | Executive Sponsor | Principal Consultant | Project Manager | Technical Consultants | Solutions Engineer | Solutions Consultant | Full-Stack Developers | Account Manager | Finance Lead
PRIORITY | ACTIVITY | Client | [8 empty] | Aptitude 8
Project Management
| Account readiness | [9 empty] | C | A | C | I | I | I | I | R | I
| Meeting scheduling | [9 empty] | C | A | R | C | C | C | C | C | I
| Task management | [9 empty] | I | A | R | R | R | R | C | I | I
| Action item follow-up | [9 empty] | I | A | R | C | C | C | C | I | I
| Scope adherence | [9 empty] | C | R | A | C | C | C | C | I | I
| Budget adherence | [9 empty] | C | R | A | C | C | C | C | I | I
| RAID log maintenance | [9 empty] | C | A | R | I | I | I | I | I | I
Account Management
| Change order management | [9 empty] | C | A | C | I | I | C | I | R | I
| Billing inquiries & updates | [9 empty] | I | C | C | I | I | I | I | A | R
| Expansions | [9 empty] | C | A | C | I | I | C | I | R | I
| Escalations | [9 empty] | R | C | C | C | C | C | C | A | I
| Check ins | [9 empty] | C | C | A | I | I | I | I | R | I
Controls & Approvals
| Requirements sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| TRD/BRD sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Design sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Change order sign-off | [9 empty] | I | A | C | I | I | I | I | R | I
| UAT completion sign-off | [9 empty] | I | C | A | C | C | R | I | I | I
| Training sign-off | [9 empty] | I | C | A | C | C | R | I | I | I
| Deployment sign-off | [9 empty] | I | R | A | C | C | C | I | I | I
| Project closure | [9 empty] | C | R | A | I | I | I | I | R | I
Workstream owners (Epics)
| Data architecture | [9 empty] | I | A | C | R | R | C | I | I | I
| Integrations | [9 empty] | I | R | C | A | R | C | C | I | I
| Migrations | [9 empty] | I | R | C | A | R | C | C | I | I
| Sales | [9 empty] | I | A | C | R | C | R | C | I | I
| Marketing | [9 empty] | I | A | C | R | C | R | C | I | I
| Service | [9 empty] | I | A | C | R | C | R | C | I | I
| Operations | [9 empty] | I | A | C | R | C | R | C | I | I
| Training | [9 empty] | I | A | C | C | C | R | C | I | I
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## RACI Matrix (internal use) (hidden)
Services RACI MATRIX
|  | CEO | CXO | Director of Delivery | CRO | COO | Project Manager | Delivery Lead | Consultants | Developer | Account Executive | Solutions Architect (Pre-Sale) | Solutions Engineer (Post-Sale) | Contractor
PRIORITY | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  | Additional Resources
Pre-Sales Through Kickoff
Low |  |  | R |  |  |  | R | A |  | C
Medium | [6 empty] | R
High |  | I |  |  |  |  | A | A | A | C |  |  | C
R
NOW Project
| Agenda/Recap | C | C |  |  |  | R | C | C | C |  |  | C
| Task Status Maintenance | I | I | I | I |  | R | C | C | C | C | C | C
| Due Date Changes | I | I | I |  |  | R |  |  |  | I | I | I
Meeting Scheduling
Task Execution
Budget Maintenance
Client Comms
NEXT Project (retainer)
|  | C | C | C | C |  |  | R | R | R | A
|  | I | I | I | I |  | A | A | A | A
PHASE 4
| Perform Change Management |  | C | C | C |  | R | A | A | A
PHASE 5
| Create Lessons Learned | C | C | C | C |  | R | C | C | C | C | C | C
| Create Project Closure Report | I | I | I | I |  | A | I | I | I | I | I | I
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## RACI Matrix (External Use) (hidden)
Services RACI MATRIX
|  | Project Sponsor | CXO | Director of Delivery | Sales Leadership (CRO) | Operations | Project Manager | Delivery Lead | Consultants | Developer | Account Executive | Solutions Architect(Pre-Sale) | Solutions Engineer(Post-Sale) | Contractor | Role 5
PRIORITY | PROJECT DELIVERABLE / ACTIVITY | Project Leadership |  |  |  |  | Project Team Members |  |  |  | Additional Resources
Pre-Sales Through Kickoff
Low |  |  | R |  |  |  | R | A |  | C
Medium | [6 empty] | R
High |  | I |  |  |  |  | A | A | A | C |  |  | C
R
NOW Project
| Agenda/Recap | C | C |  |  |  | R | C | C | C |  |  | C
| Task Status Maintenance | I | I | I | I |  | R | C | C | C | C | C | C
| Due Date Changes | I | I | I |  |  | R |  |  |  | I | I | I
Meeting Scheduling
Task Execution
Budget Maintenance
Client Comms
NEXT Project (retainer)
|  | C | C | C | C |  |  | R | R | R | A
|  | I | I | I | I |  | A | A | A | A
Project Close Out
|  |  | C | C | C |  | R | A | A | A
PHASE 5
|  | C | C | C | C |  | R | C | C | C | C | C | C
|  | I | I | I | I |  | A | I | I | I | I | I | I
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Draft - Process Focus (hidden)
Services RACI MATRIX
|  | Executive Sponsor | Project Management | Marketing Team Lead | Services Team Lead | Technical Lead | Project Management | Accounts Payable | Director of Delivery | Principal Consultant | Project Manager | Technical Consultants | Solutions Engineer | Solutions Consultants | Full-Stack Developers | Account Manager | Head of Finance
PRIORITY | PROJECT DELIVERABLE / ACTIVITY | Client | [6 empty] | Aptitude 8
Project Management
| Meeting scheduling | [7 empty] | C | A | R | C | C | C | C | C | I
| Task management | [7 empty] | C | R | A | R | C | R | C | C | I
| Action item creation + accountability | [7 empty] | A | R | R | I | I | I | I | R | I
| Account readiness | [7 empty] | A | C | C | C | C | C | C | R | I
| Scope adherence | [7 empty] | C | R | A | C | C | C | C | C | I
| Budget adherence | [7 empty] | I | R | A | I | I | I | I | C | I
| RAID log maintenance | [7 empty] | C | A | R | I | I | I | I | I | I
| Change order management | [7 empty] | C | A | C | I | I | I | I | R | I
| Escalations | [7 empty] | R | C | C | C | C | C | C | A | I
| Account check-ins | [7 empty] | I | C | A | I | I | I | I | R | I
Mobilization
| Align on scope of work | [7 empty] | A | R | I | I | I | I | I | C | I
| Confirm stakeholders and SteerCo | [7 empty] | A | I | I | I | I | I | I | R | I
| Establish project governance | [7 empty] | A | R | R | I | I | I | I | R | I
| Finalize onboarding schedule | [7 empty] | A | C | C | C | C | C | C | R | I
| Conduct activation call (formal kickoff) | [7 empty] | A | R | C | C | C | C | C | R | I
| Manage billing and invoicing | [7 empty] | I | I | I | I | I | I | I | C | R
Ensuring invoices are paid | bar: A A to I I
Requirements Analysis
| Schedule discovery sessions | [7 empty] | A | C | R | C | C | C | C | I | I
| Facilitate discovery sessions | [7 empty] | A | R | C | I | I | I | I | I | I
| Gather business requirements | [7 empty] | A | R | I | C | C | C | C | I | I
Validate business requirements | bar: A A A to I I I
| Map current state processes | [7 empty] | A | R | I | C | C | C | C | I | I
Solution Design
| Translate requirements to HubSpot architecture | [7 empty] | A | R | I | C | C | C | C | I | I
| Build solution documentation | [7 empty] | A | R | I | C | C | C | C | I | I
Review proposed solutions/technical diagram | bar: A A to I I
Implementation
| Configure HubSpot objects | [7 empty] | A | R | I | C | C | C | C | I | I
| Build custom integration(s) | [7 empty] | A | C | I | I | I | I | R | I | I
| Execute on all development tasks | [7 empty] | A | C | I | C | C | C | R | I | I
Testing
| Conduct QA testing | [7 empty] | A | R | I | R | R | C | R | I | I
| Facilitate UAT with client | [7 empty] | A | R | R | C | C | C | C | I | I
| Track defects | [7 empty] | A | C | R | C | C | C | C | I | I
| Resolve defects | [7 empty] | A | R | I | R | R | R | R | I | I
| Validate E2E system functionality | [7 empty] | A | R | I | R | R | R | R | I | I
Change Management
| Deliver enablement sessions | [7 empty] | A | R | C | R | R | C | C | I | I
| Update documentation | [7 empty] | A | R | C | R | R | C | R | I | I
Review and approve documentation | bar: A A to I I
| Reinforce adoption strategies | [7 empty] | A | R | C | R | C | C | C | I | I
| Adjust configurations as needed | [7 empty] | A | R | I | R | R | C | R | I | I
Deployment
| Migrate final data | [7 empty] | A | R | I | R | R | C | R | I | I
| Cutover from legacy systems | [7 empty] | A | R | I | R | R | C | R | I | I
| Validate go-live readiness | [7 empty] | A | R | C | R | C | C | C | I | I
| Formal launch of HubSpot for production use | [7 empty] | A | R | I | R | R | C | R | I | I
Hypercare
| Monitor performance | [7 empty] | A | R | I | I | I | I | I | I | I
| Resolve post-go-live issues | [7 empty] | A | R | I | R | R | C | I | I | I
| Reinforce training | [7 empty] | A | R | I | R | R | C | I | I | I
Provide end-user feedback | bar: A A to I I
| Support end-user feedback | [7 empty] | A | R | I | R | R | C | I | I | I
Completion and Transition
| Document final state | [7 empty] | A | R | C | R | R | C | C | I | I
Review and approve final state documentation | bar: A to I
| Handoff of all assets and implementation materials | [7 empty] | A | R | C | R | R | C | I | I | I
| Confirm ongoing support plan | [7 empty] | A | C | C | I | I | I | I | R | I
| Facilitate formal project close out and handoff meeting | [7 empty] | A | C | C | C | I | I | I | R | I
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Stakeholder Register
Stakeholder Register
Name | Role/Title | Department | Organization | Email Address | Time Zone | Primary Responsibilities | Communication Channels | Escalation Path | SteerCo Membership | Notes/Risks

## SteerCo Members
Steering Committee Members
Name | Role/Title | Department | Organization | Email Address | Time Zone | Primary Responsibilities | Communication Channels | Escalation Path | SteerCo Membership | Notes/Risks
#N/A

## Dropdown Keys - Do Not Delete - (hidden)
RACI DROPDOWN KEYS
– DO NOT DELETE –
| RACI KEY | PRIORITY | STATUS | Time Zones
R | Responsible | Low | Not Started | (GMT -12:00) Eniwetok, Kwajalein
A | Accountable | Medium | In Progress | (GMT -11:00) Midway Island, Samoa
C | Consulted | High | Complete | (GMT -10:00) Hawaii
I | Informed |  | Needs Review | (GMT -9:30) Taiohae
|  |  | Approved | (GMT -9:00) Alaska
|  |  | Overdue | (GMT -8:00) Pacific Time (US & Canada)
|  |  | On Hold | (GMT -7:00) Mountain Time (US & Canada)
(GMT -6:00) Central Time (US & Canada), Mexico City
(GMT -5:00) Eastern Time (US & Canada), Bogota, Lima
(GMT -4:30) Caracas
(GMT -4:00) Atlantic Time (Canada), Caracas, La Paz
(GMT -3:30) Newfoundland
(GMT -3:00) Brazil, Buenos Aires, Georgetown
(GMT -2:00) Mid-Atlantic
(GMT -1:00) Azores, Cape Verde Islands
(GMT) Western Europe Time, London, Lisbon, Casablanca
(GMT +1:00) Brussels, Copenhagen, Madrid, Paris
(GMT +2:00) Kaliningrad, South Africa
(GMT +3:00) Baghdad, Riyadh, Moscow, St. Petersburg
(GMT +3:30) Tehran
(GMT +4:00) Abu Dhabi, Muscat, Baku, Tbilisi
(GMT +4:30) Kabul
(GMT +5:00) Ekaterinburg, Islamabad, Karachi, Tashkent
(GMT +5:30) Bombay, Calcutta, Madras, New Delhi
(GMT +5:45) Kathmandu, Pokhara
(GMT +6:00) Almaty, Dhaka, Colombo
(GMT +6:30) Yangon, Mandalay
(GMT +7:00) Bangkok, Hanoi, Jakarta
(GMT +8:00) Beijing, Perth, Singapore, Hong Kong
(GMT +8:45) Eucla
(GMT +9:00) Tokyo, Seoul, Osaka, Sapporo, Yakutsk
(GMT +9:30) Adelaide, Darwin
(GMT +10:00) Eastern Australia, Guam, Vladivostok
(GMT +10:30) Lord Howe Island
(GMT +11:00) Magadan, Solomon Islands, New Caledonia
(GMT +11:30) Norfolk Island
(GMT +12:00) Auckland, Wellington, Fiji, Kamchatka
(GMT +12:45) Chatham Islands
(GMT +13:00) Apia, Nukualofa
(GMT +14:00) Line Islands, Tokelau